## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Khaschandpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000020/2023-2024 | 867/MAAD | 04/05/2023 | 01/10/2025 | NEOGI ENTERPRISE | 168.73 | 60.34 | 35.76 | 85
2 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Laying of Distribution System at Dalal More, Gaddha More, Hindupara for Khaschandpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000009/2023-2024 | 693/MAAD | 13/04/2023 | 30/06/2024 | MILLENNIUM ENTERPRISE | 87.26 | 0 | 0 | 90
3 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Khaschandpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(2nd Call) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000053/2023-2024 | 956/MAAD | 29/05/2023 | 01/07/2025 | BEE GEE CONSTRUCTION | 218.56 | 109.16 | 49.94 | 85
4 | MALDAH | Kaliachak-I | Malda Mechanical | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tube Well No-I & II and Arsenic Iron Removal Plant at Khaschandpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001731/2023-2024 | 3389/MLMD | 31/10/2023 | 23/12/2026 | GHOSH BROTHERS... | 70.55 | 0 | 0 | 0
5 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Laying of Distribution System at Dawan Tola, Charka Tola, Maksaha Tola, Patuatola Chandpur, Haginagar Chandpur for Khaschandpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000459/2022-2023 | 575/MAAD | 28/03/2023 | 01/12/2024 | M/S TRILOCHAN CONSTRUCTION CO. | 104.23 | 67.53 | 64.79 | 100
6 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Khaschandpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000318/2022-2023 | 597/MAAD | 30/03/2023 | 14/05/2023 | M/S S.S. ENTERPRISE | 14.72 | 9.04 | 61.43 | 100
7 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Khaschandpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000263/2023-2024 | 2059/MAAD | 22/11/2023 | 01/03/2024 | HIRAK ROYCHOUDHURY | 5.02 | 0 | 0 | 100
8 | MALDAH | Kaliachak-I | Malda Mechanical | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Khaschandpur PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001011/2023-2024 | 3004427011 | 18/09/2023 | 17/12/2023 | W.B.S.E.D.C.LTD | 11.07 | 11.07 | 100 | 100
9 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 636/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 67.64 | 0 | 0 | 0
10 | MALDAH | Kaliachak-I | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | SM/17177 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Khaschandpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I | Junior Engineer-II | ORD/000238/2024-2025 | 1692/MAAD | 19/11/2024 | 01/07/2025 | BEE GEE CONSTRUCTION | 70.37 | 0 | 0 | 0
Total | [13 empty] | 818.15 | 257.14 | 31.43