## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 633/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 42.92 | 0 | 0 | 0
2 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Laying of Distribution System at Chowdhuri Tola for Mobarakpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000131/2023-2024 | 1473/MAAD | 01/08/2023 | 30/10/2023 | A. K. CONSTRUCTION | 43.94 | 36.6 | 83.3 | 95
3 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Mobarakpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000128/2023-2024 | 1471/MAAD | 01/08/2023 | 15/09/2023 | A ONE ENTERPRISE | 14.79 | 9.03 | 61.06 | 100
4 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Laying of Distribution System at Jahantola, Narasinghatola, Rabiramtola for Mobarakpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000132/2023-2024 | 1474/MAAD | 01/08/2023 | 29/09/2024 | GOBINDA ENTERPRISE | 42.15 | 30.07 | 71.35 | 92
5 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Mobarakpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda | Assistant Engineer-II | Junior Engineer-II | ORD/000130/2023-2024 | 1472/MAAD | 01/08/2023 | 01/08/2024 | M/S EHAN ENTERPRISE | 5.02 | 0 | 0 | 100
6 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Mobarakpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(3rd Call) | Assistant Engineer-II | Junior Engineer-II | ORD/000279/2023-2024 | 3081/MAAD | 14/12/2023 | 01/04/2025 | M/S PARIMAL DAS | 212.51 | 63.33 | 29.8 | 70
7 | MALDAH | Kaliachak-II | Malda Mechanical | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Mabarakpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | Assistant Engineer - II | Junior Engineer-03 | ORD/002481/2023-2024 | 97/MLMD | 11/01/2024 | 01/05/2025 | HANNAN BUILDERS PVT. LTD. | 70.67 | 24.6 | 34.81 | 50
8 | MALDAH | Kaliachak-II | Malda Mechanical | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000059/2025-2026 | 2083/MLMD | 30/04/2025 | 30/06/2025 | SUBRATA SAHA | 0.78 | 0 | 0 | 0
9 | MALDAH | Kaliachak-II | Malda Mechanical | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Quotation payment for Mobarakpur PH NO 1 & AIRP Under Mothabri CCC Under the district of Malda. |  |  | BILL/03202/2024-2025 | BP-2024-25-634 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 10.39 | 0 | 0 | 0
10 | MALDAH | Kaliachak-II | Malda Mechanical | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Quotation payment for Mobarakpur PH NO 2 Under Mothabri CCC Under the district of Malda. |  |  | BILL/02386/2025-2026 |  | 24/09/2025 | 24/09/2025 | W.B.S.E.D.C.LTD | 18.44 | 0 | 0 | 0
11 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Mobarakpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(3rd Call) | Assistant Engineer-II | Junior Engineer-II | ORD/000278/2023-2024 | 3080/MAAD | 14/12/2023 | 01/07/2025 | M/S PARIMAL DAS | 168.04 | 8.55 | 5.09 | 80
12 | MALDAH | Kaliachak-II | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | SM/17178 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Mobarakpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000242/2024-2025 | 1696/MAAD | 19/11/2024 | 01/07/2025 | BINA CONSTRUCTION | 66.6 | 0 | 0 | 0
Total | [13 empty] | 696.25 | 172.19 | 24.73