## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site at Deonapur Piped Water Supply Scheme at Kaliachak-lll Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000092/2023-2024 | 1376/MAAD | 13/07/2023 | 11/09/2023 | TROYEE | 5 | 0 | 0 | 0
2 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Route servey & design for prepration of DPR of Deonapur, Saidpur & Mobarakpur Piped Water Supply Scheme at Kaliachak - III & Kaliachak - II Development Block under Malda Arsenic Area W/S Division, PHE Dte. in the district of Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000250/2023-2024 | 1764/MAAD | 30/09/2023 | 15/10/2023 | FUTURE | 0.99 | 0.99 | 100 | 100
3 | MALDAH | Kaliachak-III | Malda Mechanical | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001905/2023-2024 | 3004364433 | 31/07/2023 | 29/10/2023 | W.B.S.E.D.C.LTD | 5.51 | 5.51 | 100 | 100
4 | MALDAH | Kaliachak-III | Malda Mechanical | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001904/2023-2024 | 3004364419 | 31/07/2023 | 29/10/2023 | W.B.S.E.D.C.LTD | 4.24 | 4.24 | 100 | 100
5 | MALDAH | Kaliachak-III | Malda Mechanical | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001903/2023-2024 | 3004364426 | 31/07/2023 | 29/10/2023 | W.B.S.E.D.C.LTD | 6.35 | 6.35 | 100 | 100
6 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 625/MAAD | 05/04/2023 | 05/04/2023 | Resource Division | 190.2 | 0 | 0 | 0
7 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Laying of Distribution System for and other allied works at Ainul Hut under Deonapur Piped Water supply scheme of Kaliachak-III Block of Southern Sector at under Malda Arsenic Area W/S Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000095/2023-2024 | 1378/MAAD | 13/07/2023 | 11/09/2023 | USHA ENTERPRISE | 80.37 | 66.6 | 82.87 | 84
8 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Laying of Distribution System for and other allied works at Bakrabad Char under Deonapur Piped Water supply scheme of Southern Sector at under Malda Arsenic Area W/S Division, P.H.E. Dte. (Kaliachak-III). | Assistant Engineer-II | Junior Engineer-III | ORD/000099/2023-2024 | 1379/MAAD | 13/07/2023 | 12/12/2023 | A. B. CONSTRUCTION | 57.65 | 41.26 | 71.57 | 80
9 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (3RD Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda.(2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000102/2023-2024 | 1382/MAAD | 13/07/2023 | 27/08/2023 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.64 | 5.05 | 66.15 | 100
10 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (2ND Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda. (2nd Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000101/2023-2024 | 1381/MAAD | 13/07/2023 | 27/08/2023 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.65 | 4.89 | 63.94 | 100
11 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (Head Work Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000094/2023-2024 | 1377/MAAD | 13/07/2023 | 27/08/2023 | MD. TALEB ALI | 7.65 | 5.97 | 78.05 | 100
12 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Deonapur Piped Water Supply Scheme at Kaliachak-lll Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000390/2023-2024 | 1375/MAAD | 13/07/2023 | 28/10/2023 | MADHUMITA ENTERPRISE | 4.99 | 4.16 | 83.25 | 100
13 | MALDAH | Kaliachak-III | Malda Mechanical | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I, II & III and Arsenic Iron Removal Plant at Deonapur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018102) | Assistant Engineer - II | Junior Engineer-03 | ORD/000666/2023-2024 | 2691/MLMD | 11/08/2023 | 22/01/2026 | GHOSH BROTHERS... | 82.34 | 0 | 0 | 0
14 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Deonapur Piped Water supply scheme of Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) | Assistant Engineer-II | Junior Engineer-III | ORD/000257/2023-2024 | 1991/MAAD | 02/11/2023 | 30/01/2025 | WATER TECH | 216.09 | 0 | 0 | 75
15 | MALDAH | Kaliachak-III | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | SM/18232 | New | Construction of 700 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Deonapur Piped Water Supply scheme at Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-III | ORD/000265/2023-2024 | 3025/MAAD | 07/12/2023 | 01/09/2025 | BANIK BROTHERS | 299.38 | 46.62 | 15.57 | 60
Total | [13 empty] | 976.04 | 191.64 | 19.63