## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2023 to 31.12.2023) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000337/2022-2023 | 2294/MAAD | 28/12/2022 | 28/12/2023 | M/S PARIMAL DAS | 1.73 | 2.57 | 148.47 | 100
2 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 08/09/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 2675.2 | 11.18 | 60
3 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Surveying, Design, Engineering, Supplying, Construction, Erection, Testing, Commissioning of Raw Water Intake Jetty Structure (Fixed type) with Pump House over river Fulhar near Mathurapur connected by carriageway with Pump House & the river bank including River Bank protection, Laying of Raw Water Rising Mains, Conventional type Water Treatment Plant (treated water Capacity 87 MLD) with centralized SCADA system, Substation Buildings at Intake as well as at WTP including all Electrical and Mech. work (at Intake and WTP and Boosting Station II at Shyamdaspur), 3500 Cum capacity Clear Water Reservoir at WTP site, High Lift Pump House, Clear Water Rising Mains from WTP to Clear Water Reservoirs at Boosting Station-I( at Niamatpur) & II (at shyamdaspur) and Boosting Stations to different Zonal OHR New and Existing)sites Kaliachak-I,II and Englishbazar Block, 500 Cum capacity Clear Water Reservoir at Booster Station-I at Niamatpur under Englishbazar block and another 3500 Cum capacity Clear Water Reservoir at Boosting Station-II at Shyamdaspur under Kaliachak-II block, Internal pathway, surface Drain, Staff Quarter including all related and allied Civil, Mechanical, Electrical and Instrumentational work on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 3(Three) months Trial Run along with Operation & Maintenance for 5(five) years for AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Malda Arsenic Affected Area (Northern & Southern Sector) at District Malda under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000169/2023-2024 | 1527/MAAD | 14/08/2023 | 30/06/2026 | GBC INFRASTRUCTURE PRIVATE LIMITED | 30211.99 | 9119.04 | 30.18 | 40
4 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Formal Work Order for Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries at Boosting Pumping Station, Niyamatpur ( for Zonal OHRS of English Bazar Block) under Augmentation of Surface Water Based Piped Water Supply Scheme (Northeren Sector), District - Malda, PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000908/2023-2024 | 2667/MLMD | 10/08/2023 | 06/02/2024 | ORIENTAL ENGINEERING CO. | 546.37 | 0 | 0 | 0
5 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.09.2023 to 02.03.2024) | Assistant Engineer-II | Junior Engineer-IV | ORD/000215/2023-2024 | 1552/MAAD | 18/08/2023 | 18/02/2024 | UNITED ENGINEERS CORPORATION | 0.87 | 2.15 | 245.54 | 0
6 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Modification of existing High Lift pumping station and Sub-station at Mathurapur (for Zonal OHRS of Manikchak Block) under Augmentation of Surface Water Based Piped Water Supply Scheme (Northern Sector) Dist. Malda, PHE Dte. | Assistant Engineer - II | Junior Engineer-04,Junior Engineer-07 | ORD/001538/2023-2024 | 2669/MLMD | 10/08/2023 | 26/01/2026 | WEST BENGAL ENGINEERING COMPANY. | 353.77 | 63.47 | 17.94 | 73
7 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Continuation Work Order for Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(for the period from 01.01.2024 to 30.12.2024)= 365 days | Assistant Engineer-I | Junior Engineer-I | ORD/000298/2023-2024 | 3290/MAAD | 29/12/2023 | 28/12/2024 | NITAI PANDEY | 1.73 | 3.9 | 224.94 | 10
8 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Continuation Work Order for Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. (for the period from 01.01.2024 to 30.12.2024)= 365 days. | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II | ORD/000297/2023-2024 | 3289/MAAD | 29/12/2023 | 28/12/2024 | SUBRATA SAHA | 1.73 | 4.43 | 255.62 | 40
9 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 494/MAAD | 23/03/2023 | 23/03/2023 | Resource Division | 13510.42 | 0 | 0 | 0
10 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1716/MAAD | 21/09/2023 | 21/09/2023 | Resource Division | 21.3 | 0 | 0 | 0
11 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1973/MAAD | 30/10/2023 | 30/10/2023 | Resource Division | 20.22 | 0 | 0 | 0
12 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000068/2024-2025 | 1343/MLMD | 26/04/2024 | 26/06/2024 | NITAI PANDEY | 0.78 | 0.76 | 98.57 | 0
13 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Supply of different DI materials for the work of "Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II& III Blocks in the district of Malda." | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000134/2024-2025 | 1163/MAAD | 07/06/2024 | 27/02/2025 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 76.96 | 0 | 0 | 50
14 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for BAHIRBONAScheme (Capacity-450 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000236/2024-2025 | 816/MAAD | 22/04/2024 | 22/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
15 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for MOHABBATPUR Scheme (Capacity-500 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000232/2024-2025 | 739/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
16 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for SULTANGANJ Scheme (Capacity-600 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000235/2024-2025 | 815/MAAD | 22/04/2024 | 22/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
17 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for MOKSADPUR Scheme (Capacity-1250 cum) in Kaliachak-I Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000237/2024-2025 | 817/MAAD | 22/04/2024 | 22/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
18 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for UTTAR CHANDIPUR Scheme (Capacity-750 cum) in English Bazar Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000230/2024-2025 | 737/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 100
19 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for SATANGAPARA Scheme (Capacity-600 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000231/2024-2025 | 738/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
20 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for JAYENPUR Scheme (Capacity-400 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000234/2024-2025 | 814/MAAD | 22/04/2024 | 22/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
21 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for CHARIANANTAPUR Scheme (Capacity-500 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000233/2024-2025 | 740/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
22 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for BRAHMONGRAM Scheme (Capacity-450 cum) in Manikchak Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000228/2024-2025 | 735/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 100
23 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for PASCHIMNARAYANPUR Scheme (Capacity-300 cum) in Manikchak Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000229/2024-2025 | 736/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
24 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1612/MAAD | 04/10/2024 | 04/10/2024 | Resource Division | 125.49 | 0 | 0 | 0
25 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1032/MAAD | 16/05/2024 | 16/05/2024 | Resource Division | 1906.64 | 0 | 0 | 0
26 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 216/MAAD | 23/02/2024 | 23/02/2024 | Resource Division | 2555.83 | 0 | 0 | 0
27 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Restoration of damaged PWD road for Chainage 18.00 KM to 220..00 Km to 30.00 KM and chainage 30.00 KM to 32.50 KM in Laying of water rising main at SH-10 under Augmentation of surface water based piped water supply scheme for Malda Arsenic Area (Northern & Southern Sector). |  |  | BILL/00081/2024-2025 | C062409333417 | 11/06/2024 | 11/06/2024 | EXUCUTIVE ENGINEER PWD MALDA | 54.95 | 0 | 0 | 0
28 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Quotation the shifting of LTOH line above newly constructing pipe line. |  |  | BILL/00645/2023-2024 | C022455072524 | 20/02/2024 | 20/02/2024 | W.B.S.E.D.C.LTD | 0.81 | 0 | 0 | 0
29 | MALDAH |  | Malda Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | The payment to WBSRDA against the repair of damaged roads. |  |  | BILL/00732/2024-2025 |  | 11/11/2024 | 11/11/2024 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 6 | 0 | 0 | 0
30 | MALDAH |  | Malda Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Payment for rural road damage pipe line. |  |  | BILL/00803/2024-2025 | BP-2024-25-380 | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 6 | 0 | 0 | 0
31 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Formal work order for Installation of 33KV terminal arrangement with 36KV indoor type equipments (non-extensible type) with VCB, CT, PT etc. at Sub-Station of Shyamdaspur Boosting Station for augmentation of PWSS for Malda Arsenic Affected Area at District Malda (Northern & Southern Sector). | Assistant Engineer - II | Junior Engineer-04 | ORD/001612/2024-2025 | 1693/MLMD | 28/03/2025 | 28/06/2025 | ORIENTAL ENGINEERING CO. | 38.62 | 0 | 0 | 0
32 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Formal work order for Installation of 33KV terminal arrangement with 36KV indoor type equipments (non-extensible type) with VCB, CT, PT etc. at Sub-Station of Mathurapur WTP site for augmentation of PWSS for Malda Arsenic Affected Area at District Malda (Northern & Southern Sector). | Assistant Engineer - II | Junior Engineer-04 | ORD/001613/2024-2025 | 1694/MLMD | 28/03/2025 | 28/06/2025 | WEST BENGAL ENGINEERING COMPANY. | 38.92 | 0 | 0 | 0
33 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 617/MAAD | 25/04/2025 | 25/04/2025 | Resource Division | 341.21 | 0 | 0 | 0
34 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2025-2026 | 628/MAAD | 29/04/2025 | 29/04/2025 | Resource Division | 1181.07 | 0 | 0 | 0
35 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Payment of Wayleave facility charges ID- ER-MLDT-2024-WL-44 Station- KTJ-JMQ Mast No- 275/25-27 & 275/26-28 |  |  | BILL/00414/2024-2025 | C012536185547 | 17/01/2025 | 17/01/2025 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 7.27 | 0 | 0 | 0
36 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Payment of Wayleave facility charges ID- ER-MLDT-2024-WL-42 Station - KTJ - CMX Mast No- 270/30-32 & 270/29-31 |  |  | BILL/00416/2024-2025 | C012536174759 | 17/01/2025 | 17/01/2025 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 14.88 | 0 | 0 | 0
37 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | W.B.S.E.D.C.LTD Quotation charge for Bulk power supply at Mathurapur WTP, in the dist of Malda. |  |  | BILL/02383/2025-2026 |  | 24/09/2025 | 24/09/2025 | W.B.S.E.D.C.LTD | 226.8 | 0 | 0 | 0
38 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Payment of Wayleave facility charges ID-ER-MLDT-2024-WL-43 Station- KTJ-JMQ Mast No- 276/31-33 & 277/01-02 |  |  | BILL/00415/2024-2025 | C012536178062 | 17/01/2025 | 17/01/2025 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 5.75 | 0 | 0 | 0
39 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Quotation for Service Connection charges for bulk power supply at Sankaritolaghat intake Pumping station under Malda Mechanical Division, PHE Dte for an ultimate Contract demand of ent570KVA. |  |  | BILL/01248/2025-2026 | 124 | 07/08/2025 | 07/08/2025 | W.B.S.E.D.C.LTD | 51.32 | 0 | 0 | 0
Total | [13 empty] | 75245.67 | 11884.51 | 15.79