## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Formal Work Order for Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries at Boosting Pumping Station, Niyamatpur ( for Zonal OHRS of English Bazar Block) under Augmentation of Surface Water Based Piped Water Supply Scheme (Northeren Sector), District - Malda, PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000908/2023-2024 | 2667/MLMD | 10/08/2023 | 06/02/2024 | ORIENTAL ENGINEERING CO. | 546.37 | 0 | 0 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 494/MAAD | 23/03/2023 | 23/03/2023 | Resource Division | 13510.42 | 0 | 0 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1716/MAAD | 21/09/2023 | 21/09/2023 | Resource Division | 21.3 | 0 | 0 | 0
4 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1973/MAAD | 30/10/2023 | 30/10/2023 | Resource Division | 20.22 | 0 | 0 | 0
5 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.09.2023 to 02.03.2024) | Assistant Engineer-II | Junior Engineer-IV | ORD/000215/2023-2024 | 1552/MAAD | 18/08/2023 | 18/02/2024 | UNITED ENGINEERS CORPORATION | 0.87 | 2.15 | 245.54 | 0
6 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2023 to 31.12.2023) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000337/2022-2023 | 2294/MAAD | 28/12/2022 | 28/12/2023 | M/S PARIMAL DAS | 1.73 | 2.57 | 148.47 | 100
7 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000068/2024-2025 | 1343/MLMD | 26/04/2024 | 26/06/2024 | NITAI PANDEY | 0.78 | 0.76 | 98.57 | 0
8 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for BAHIRBONAScheme (Capacity-450 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000236/2024-2025 | 816/MAAD | 22/04/2024 | 22/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
9 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for MOHABBATPUR Scheme (Capacity-500 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000232/2024-2025 | 739/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
10 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for SULTANGANJ Scheme (Capacity-600 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000235/2024-2025 | 815/MAAD | 22/04/2024 | 22/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
11 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for MOKSADPUR Scheme (Capacity-1250 cum) in Kaliachak-I Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000237/2024-2025 | 817/MAAD | 22/04/2024 | 22/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
12 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for UTTAR CHANDIPUR Scheme (Capacity-750 cum) in English Bazar Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000230/2024-2025 | 737/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 100
13 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for SATANGAPARA Scheme (Capacity-600 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000231/2024-2025 | 738/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
14 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for JAYENPUR Scheme (Capacity-400 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000234/2024-2025 | 814/MAAD | 22/04/2024 | 22/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
15 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for CHARIANANTAPUR Scheme (Capacity-500 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000233/2024-2025 | 740/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
16 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for BRAHMONGRAM Scheme (Capacity-450 cum) in Manikchak Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000228/2024-2025 | 735/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 100
17 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for PASCHIMNARAYANPUR Scheme (Capacity-300 cum) in Manikchak Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | Assistant Engineer-II | Junior Engineer-III | ORD/000229/2024-2025 | 736/MAAD | 19/04/2024 | 19/05/2024 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100 | 5
18 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1612/MAAD | 04/10/2024 | 04/10/2024 | Resource Division | 125.49 | 0 | 0 | 0
19 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1032/MAAD | 16/05/2024 | 16/05/2024 | Resource Division | 1906.64 | 0 | 0 | 0
20 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 216/MAAD | 23/02/2024 | 23/02/2024 | Resource Division | 2555.83 | 0 | 0 | 0
21 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Restoration of damaged PWD road for Chainage 18.00 KM to 220..00 Km to 30.00 KM and chainage 30.00 KM to 32.50 KM in Laying of water rising main at SH-10 under Augmentation of surface water based piped water supply scheme for Malda Arsenic Area (Northern & Southern Sector). |  |  | BILL/00081/2024-2025 | C062409333417 | 11/06/2024 | 11/06/2024 | EXUCUTIVE ENGINEER PWD MALDA | 54.95 | 0 | 0 | 0
22 | MALDAH |  | Malda Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | The payment to WBSRDA against the repair of damaged roads. |  |  | BILL/00732/2024-2025 |  | 11/11/2024 | 11/11/2024 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 6 | 0 | 0 | 0
23 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Quotation the shifting of LTOH line above newly constructing pipe line. |  |  | BILL/00645/2023-2024 | C022455072524 | 20/02/2024 | 20/02/2024 | W.B.S.E.D.C.LTD | 0.81 | 0 | 0 | 0
24 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 10/06/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 2675.2 | 11.18 | 30
25 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Modification of existing High Lift pumping station and Sub-station at Mathurapur (for Zonal OHRS of Manikchak Block) under Augmentation of Surface Water Based Piped Water Supply Scheme (Northern Sector) Dist. Malda, PHE Dte. | Assistant Engineer - II | Junior Engineer-04,Junior Engineer-07 | ORD/001538/2023-2024 | 2669/MLMD | 10/08/2023 | 30/07/2025 | WEST BENGAL ENGINEERING COMPANY. | 353.77 | 63.47 | 17.94 | 73
26 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Continuation Work Order for Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(for the period from 01.01.2024 to 30.12.2024)= 365 days | Assistant Engineer-I | Junior Engineer-I | ORD/000298/2023-2024 | 3290/MAAD | 29/12/2023 | 28/12/2024 | NITAI PANDEY | 1.73 | 3.9 | 224.94 | 10
27 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Continuation Work Order for Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. (for the period from 01.01.2024 to 30.12.2024)= 365 days. | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II | ORD/000297/2023-2024 | 3289/MAAD | 29/12/2023 | 28/12/2024 | SUBRATA SAHA | 1.73 | 4.43 | 255.62 | 40
28 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Formal work order for Installation of 33KV terminal arrangement with 36KV indoor type equipments (non-extensible type) with VCB, CT, PT etc. at Sub-Station of Shyamdaspur Boosting Station for augmentation of PWSS for Malda Arsenic Affected Area at District Malda (Northern & Southern Sector). | Assistant Engineer - II | Junior Engineer-04 | ORD/001612/2024-2025 | 1693/MLMD | 28/03/2025 | 28/06/2025 | ORIENTAL ENGINEERING CO. | 38.62 | 0 | 0 | 0
29 | MALDAH |  | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Formal work order for Installation of 33KV terminal arrangement with 36KV indoor type equipments (non-extensible type) with VCB, CT, PT etc. at Sub-Station of Mathurapur WTP site for augmentation of PWSS for Malda Arsenic Affected Area at District Malda (Northern & Southern Sector). | Assistant Engineer - II | Junior Engineer-04 | ORD/001613/2024-2025 | 1694/MLMD | 28/03/2025 | 28/06/2025 | WEST BENGAL ENGINEERING COMPANY. | 38.92 | 0 | 0 | 0
30 | MALDAH |  | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | SM/18660 | Augmentation | Supply of different DI materials for the work of "Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II& III Blocks in the district of Malda." | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000134/2024-2025 | 1163/MAAD | 07/06/2024 | 27/02/2025 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 76.96 | 0 | 0 | 50
Total | [13 empty] | 43199.37 | 2765.46 | 6.4