## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. | SM/13237 | Augmentation | Additional work of Improvement of Existing 2 x 250 KVA Substation (11/0.433KV) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/001594/2023-2024 | 3216/MLMD | 05/10/2023 | 19/10/2023 | M/S P.P. ELECTRICALS | 4.47 | 0 | 0 | 100
2 | MALDAH |  | Malda Mechanical | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. | SM/13237 | Augmentation | Formal work order for the work of "Improvement of existing 2 x 250 KVA Substation (11/0.433 KV) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, PHE Dte." | Assistant Engineer - II | Junior Engineer-04 | ORD/000900/2022-2023 | 2736/MLMD | 05/12/2022 | 01/02/2025 | M/S P.P. ELECTRICALS | 115.25 | 0 | 0 | 100
Total | [13 empty] | 119.72 | 0 | 0