## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Gourhanda Water Supply Schemes at Chanchal-II Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | Assistant Engineer - II | Junior Engineer-05 | ORD/000205/2023-2024 | 2136/MLMD | 07/07/2023 | 03/10/2028 | MAA BHABOTARINE ENTERPRISE. | 6.97 | 0 | 0 | 0
2 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Laxmighat Water Supply Schemes at Ratua-II Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000194/2023-2024 | 2140/MLMD | 07/07/2023 | 03/10/2028 | MAA BHABOTARINE ENTERPRISE. | 6.97 | 0 | 0 | 0
3 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Dhanjana and adjacent Water Supply Schemes at Chanchal-I Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | Assistant Engineer - II | Junior Engineer-05 | ORD/000204/2023-2024 | 2137/MLMD | 07/07/2023 | 03/10/2028 | EQUIPMENTS AND SPARES AGENCIES | 41.76 | 0 | 0 | 0
4 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Arapur Water Supply Schemes at English Bazar Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | Assistant Engineer - II |  | ORD/000747/2023-2024 | 2812/MLMD | 17/08/2023 | 13/11/2028 | NIRMAN. | 13.54 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Adhna and adjacent Water Supply Schemes at Gazole Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | Assistant Engineer - II | Junior Engineer-07 | ORD/000203/2023-2024 | 2138/MLMD | 07/07/2023 | 03/10/2028 | DEY ENTERPRISE.. | 21.11 | 0 | 0 | 83
6 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Arjuna and adjacent Water Supply Schemes at Harishchandrapur-II Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | Assistant Engineer - II | Junior Engineer-05 | ORD/001833/2023-2024 | 3631/MLMD | 23/11/2023 | 19/02/2029 | DILIP MAHATO. | 33.85 | 0 | 0 | 83
7 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Arapur Water Supply Schemes at English Bazar Block in the district of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000465/2024-2025 | 3830/MLMD | 02/12/2024 | 02/03/2025 | DILIP MAHATO. | 13.54 | 0 | 0 | 0
8 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Habibpur and adjacent Water Supply Schemes at Habibpur Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000202/2023-2024 | 2139/MLMD | 07/07/2023 | 03/10/2028 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 35.2 | 0 | 0 | 82
9 | MALDAH |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division | SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Mahammadpur and adjacent Water Supply Schemes at Old Malda Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-07 | ORD/000746/2023-2024 | 2811/MLMD | 17/08/2023 | 13/11/2028 | SWITCHING AVO ELECTRO POWER LTD | 34.83 | 0 | 0 | 20
Total | [13 empty] | 207.77 | 0 | 0