## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani | SM/19225 | Augmentation | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 8 nos Distribution Zone (OHR SITE) within Manikchak Block under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000469/2024-2025 | 3852/MLMD | 03/12/2024 | 01/06/2025 | MACHINE SUPPLIERS SYNDICATE (P) LTD. | 341.1 | 0 | 0 | 0
2 | MALDAH |  | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani | SM/19225 | Augmentation | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 7 nos Distribution Zone (OHR SITE) within Kaliachak Block-I under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-04,Junior Engineer-07 | ORD/000546/2024-2025 | 4083/MLMD | 16/12/2024 | 14/06/2025 | CREATIVE WATER & PROCESS TECH. PVT. LTD. | 298.3 | 0 | 0 | 0
3 | MALDAH |  | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani | SM/19225 | Augmentation | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 5 nos Distribution Zone (OHR SITE) within Englishbazar Block under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-04,Junior Engineer-07 | ORD/000545/2024-2025 | 4082/MLMD | 16/12/2024 | 14/06/2025 | EASTERN INDIA SALES & SERVICE. | 212.97 | 0 | 0 | 0
4 | MALDAH |  | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani | SM/19225 | Augmentation | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 18 nos Distribution Zone (OHR SITE) within Kaliachak Block-III under Augmentation of Malda Arsenic Area W/S scheme (Southern Sector) under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000484/2024-2025 | 3894/MLMD | 05/12/2024 | 03/06/2025 | ORIENTAL ENGINEERING CO. | 765.98 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani | SM/19225 | Augmentation | Formal work order for Various electro-mechanical works for existing High Lift pumping station at Dariapur under Augmentation of Malda Arsenic Area W/S scheme (Southern Sector) under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000486/2024-2025 | 3911/MLMD | 06/12/2024 | 04/06/2025 | ALPHA ENTERPRISE. | 153.89 | 0 | 0 | 0
6 | MALDAH |  | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani | SM/19225 | Augmentation | Supply, Installation & commissioning of Secondary gaseous chlorination arrangement and other allied works for 2 nos Distribution Zone (OHR site) within Manikchak and English bazar Block under Augmentation of Malda Arsenic Area Water Supply Scheme (Northern Sector), under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/001322/2024-2025 | 1084/MLMD | 12/02/2025 | 13/05/2025 | SHREE BISHNU CONSTRUCTION | 81.51 | 0 | 0 | 0
Total | [13 empty] | 1853.74 | 0 | 0