## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Resource | Supply of spare parts including calibration and regular upkeep of onsite mobile analysis system (OMAS) used for drinking water quality monitoring in arsenic and iron removal plants (AIRPs). | SM/11210 | Support-WQMSP | Annual Maintenance Contract (AMC) including supply of Spare Parts for On-site Mobile Analysis System (OMAS) installed in various Water Testing Laboratories of PHE Dte., Govt. of West Bengal from 29/08/2023 to 29/02/2024 | Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 2624/RS | 25/08/2023 | 26/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 68.21 | 0 | 0 | 79
2 | MURSHIDABAD |  | Resource | Supply of spare parts including calibration and regular upkeep of onsite mobile analysis system (OMAS) used for drinking water quality monitoring in arsenic and iron removal plants (AIRPs). | SM/11210 | Support-WQMSP | Annual Maintenance Contract (AMC) including supply of Spare Parts for On-site Mobile Analysis System (OMAS) installed in various Water Testing Laboratories of PHE Dte., Govt. of West Bengal from 29/08/2023 to 29/02/2024 | Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 2624/RS | 25/08/2023 | 26/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 68.21 | 0 | 0 | 79
3 | NADIA |  | Resource | Supply of spare parts including calibration and regular upkeep of onsite mobile analysis system (OMAS) used for drinking water quality monitoring in arsenic and iron removal plants (AIRPs). | SM/11210 | Support-WQMSP | Annual Maintenance Contract (AMC) including supply of Spare Parts for On-site Mobile Analysis System (OMAS) installed in various Water Testing Laboratories of PHE Dte., Govt. of West Bengal from 29/08/2023 to 29/02/2024 | Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 2624/RS | 25/08/2023 | 26/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 68.21 | 0 | 0 | 79
4 | NORTH 24 PARGANAS |  | Resource | Supply of spare parts including calibration and regular upkeep of onsite mobile analysis system (OMAS) used for drinking water quality monitoring in arsenic and iron removal plants (AIRPs). | SM/11210 | Support-WQMSP | Annual Maintenance Contract (AMC) including supply of Spare Parts for On-site Mobile Analysis System (OMAS) installed in various Water Testing Laboratories of PHE Dte., Govt. of West Bengal from 29/08/2023 to 29/02/2024 | Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 2624/RS | 25/08/2023 | 26/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 68.21 | 0 | 0 | 79
5 | MALDAH |  | Resource | Supply of spare parts including calibration and regular upkeep of onsite mobile analysis system (OMAS) used for drinking water quality monitoring in arsenic and iron removal plants (AIRPs). | SM/11210 | Support-WQMSP | Supply of Spare Parts including Calibration & regular upkeep of On-site Mobile Analysis System (OMAS) used for drinking water quality monitoring in Arsenic & Iron Removal Plants (AIRPs) related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 6(Six) months from 17/10/2023 to 16/04/2024. | Assistant Engineer | Junior Engineer | ORD/000213/2023-2024 | 3148/RS | 12/10/2023 | 12/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.41 | 0 | 0 | 98
6 | MURSHIDABAD |  | Resource | Supply of spare parts including calibration and regular upkeep of onsite mobile analysis system (OMAS) used for drinking water quality monitoring in arsenic and iron removal plants (AIRPs). | SM/11210 | Support-WQMSP | Supply of Spare Parts including Calibration & regular upkeep of On-site Mobile Analysis System (OMAS) used for drinking water quality monitoring in Arsenic & Iron Removal Plants (AIRPs) related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 6(Six) months from 17/10/2023 to 16/04/2024. | Assistant Engineer | Junior Engineer | ORD/000213/2023-2024 | 3148/RS | 12/10/2023 | 12/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.41 | 0 | 0 | 98
7 | NADIA |  | Resource | Supply of spare parts including calibration and regular upkeep of onsite mobile analysis system (OMAS) used for drinking water quality monitoring in arsenic and iron removal plants (AIRPs). | SM/11210 | Support-WQMSP | Supply of Spare Parts including Calibration & regular upkeep of On-site Mobile Analysis System (OMAS) used for drinking water quality monitoring in Arsenic & Iron Removal Plants (AIRPs) related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 6(Six) months from 17/10/2023 to 16/04/2024. | Assistant Engineer | Junior Engineer | ORD/000213/2023-2024 | 3148/RS | 12/10/2023 | 12/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.41 | 0 | 0 | 98
8 | NORTH 24 PARGANAS |  | Resource | Supply of spare parts including calibration and regular upkeep of onsite mobile analysis system (OMAS) used for drinking water quality monitoring in arsenic and iron removal plants (AIRPs). | SM/11210 | Support-WQMSP | Supply of Spare Parts including Calibration & regular upkeep of On-site Mobile Analysis System (OMAS) used for drinking water quality monitoring in Arsenic & Iron Removal Plants (AIRPs) related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 6(Six) months from 17/10/2023 to 16/04/2024. | Assistant Engineer | Junior Engineer | ORD/000213/2023-2024 | 3148/RS | 12/10/2023 | 12/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.41 | 0 | 0 | 98
Total | [13 empty] | 434.48 | 0 | 0