## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | SM/07200 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RADHARGHAT-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000507/2021-2022 | 342/BSD | 27/08/2021 | 26/09/2021 | IMAGIN | 4.17 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | SM/07200 | Retrofitting | EXTENSION OF DISTRIBUTION PIPELINE WITHIN THE COMMAND AREA OF BHALKUNDI WSS, TNO- 478/20-21/EE |  |  | VCH/002012/2020-2021 | 473/W | 08/03/2021 | 08/03/2021 | DEBASISH SARKAR | 4.64 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | SM/07200 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of SAKTIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- MAHATA, CODE-315638, TNO- 538/20-21/EE |  |  | VCH/002010/2020-2021 | 473/W | 08/03/2021 | 08/03/2021 | SO-FINE AQUARIUM | 11.52 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | SM/07200 | Retrofitting | LAYING OF UPVC PIPELINE AT JOYPUR PASCHIMPARA....BHALKUNDI Z-I WSS, TNO- 05/20-21/AEKSD |  |  | VCH/002011/2020-2021 | 473/W | 08/03/2021 | 08/03/2021 | DEBASISH SARKAR | 1.6 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | SM/07200 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chumarigacha (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000725/2020-2021 | 3122 / MURD | 09/12/2020 | 07/02/2021 | TANUSHREE ENTERPRISE | 39.34 | 0 | 0 | 1
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | SM/07200 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000453/2021-2022 | 303/BSD | 13/08/2021 | 12/09/2021 | IMAGIN | 4.34 | 4.34 | 100 | 0
Total | [13 empty] | 65.6 | 4.34 | 6.61