## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07276 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE |  |  | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 17/03/2021 | SAMBHUNATH ROY | 29.21 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07276 | Retrofitting | Planning, design, investigation, construction, erection, installation, completion, testing and commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & iron present in ground water in diff. connection to acceptable limit as recommended by CPHEEO manual on basis of departmental process drawing (Modified Sujapur Sadipur Model) incld. 3 months Trail Run & 9 months O&M of diff. blocks in the district of Murshidabad, PHE Dte., (JAGAIPUR W/S SCHEME) |  |  | VCH/002037/2020-2021 | 478/W | 12/03/2021 | 12/03/2021 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 27.52 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07276 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 1305 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Ballalpur ( Village Code -313811) under Ballalpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000021/2022-2023 | 1052/MURD | 25/04/2022 | 09/06/2022 | TARIKUL SK | 60.99 | 54.93 | 90.06 | 10
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07276 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 540/6/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 7.16 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07276 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/00974/2023-2024 |  | 14/12/2023 | 14/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07276 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 15/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
Total | [13 empty] | 215.6 | 54.93 | 25.48