## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SHIBPUR G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000407/2021-2022 | 249/LSD | 18/08/2021 | 17/09/2021 | IMAGIN COMMUNICATION | 4.18 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JITPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - PAR RAGHUNATHPUR, CODE- 314677 , TNO- 80/20-21/SEMC |  |  | VCH/002052/2020-2021 | 504/W | 22/03/2021 | 22/03/2021 | UMWELT ENGINEER PVT LTD | 36.66 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE |  |  | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 17/03/2021 | SAMBHUNATH ROY | 29.21 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | Operation & Maintenance of distribution system and allied works of Siddhikhali (Zone-III)Surface W/S Scheme Raghunathganj-I Block from 01.05.2019 to 29.02.2020 |  |  | VCH/000933/2020-2021 | 489/W | 17/03/2021 | 17/03/2021 | SUDIPA SINGHA ROY | 4.99 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | CONT WORK OF OPERATION & GUARDING OF PUMPING MACHINERY FOR MAHESAIL W/S SCHEME PH-I , TNO- 894/19-20/EE |  |  | VCH/002042/2020-2021 | 489/W | 17/03/2021 | 17/03/2021 | RELIABLE ENTERPRISE | 1.41 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | Additional extension of UPVC pipeline at Sankuria and Madhunia (Adibashipara) under the Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division, P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000918/2021-2022 | 361/LSD | 17/11/2021 | 01/01/2022 | SARAJIT KUMAR MAJUMDER | 4.43 | 4.42 | 99.79 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | Laying of different dia U.P.V.C Pipeline for Distribution Network (Remaining Portion) and construction of RCC Stand Post including platform at Sankuria Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001225/2021-2022 | 413/LSD | 27/12/2021 | 26/01/2022 | SARAJIT KUMAR MAJUMDER | 4.88 | 4.85 | 99.34 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (JalJeevan Mission ) "from existing Distribution system within the Command area of village AMARKUNDU (Village Code 315017) under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block in the District of Murshidabad . | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000627/2020-2021 | 2570/MURD | 01/10/2020 | 15/11/2020 | MAJUMDER CONSTRUCTION | 38.26 | 34.35 | 89.76 | 1
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) of 200 left out in connection with Jal Jeevan Mission and Jal Swapna under command area of village Amarkundu (Village code 315017) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001806/2021-2022 | 803/MURD | 24/03/2022 | 13/04/2022 | S.K. CONSTRUCTION (TABLU) | 11.79 | 0 | 0 | 0
Total | [13 empty] | 135.81 | 43.61 | 32.11