## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV | SM/07283 | Retrofitting | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 27/03/2021 | S.P CONSTRUCTION | 117.33 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV | SM/07283 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgiri (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District. |  |  | VCH/000865/2021-2022 | 221-MSD/21-22 | 09/12/2021 | 09/12/2021 | AMAL KUMAR DAS | 7.7 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV | SM/07283 | Retrofitting | Holding Awardness Programme FHTC |  |  | VCH/000866/2021-2022 | 208-MSD/21-22 | 08/12/2021 | 08/12/2021 | IMAGIN COMMUNICATION | 3.57 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV | SM/07283 | Retrofitting | Extension of pipeline at uncovered habitation of Kanthaliapara Year Ali to Fajit Sk house via Ali Box Sk house & Jalit Sk house under command area of Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. | ASSISTANT ENGINEER |  | ORD/002128/2021-2022 | 468/ISD | 03/09/2021 | 03/10/2021 | M/S. DIPTI ENTERPRISE | 3.06 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV | SM/07283 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHAR GARAMGARIDAIR(Village code 314792) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000262/2020-2021 | 259/MURD | 25/01/2021 | 11/03/2021 | AMAL KUMAR DAS | 29.36 | 0 | 0 | 0
Total | [13 empty] | 161.02 | 0 | 0