## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block(Teghori, Kasiadanga,Laxmijhola & Sekhalipur) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-B) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000068/2021-2022 | 125 /JSD | 25/05/2021 | 24/06/2021 | S.S.INFRASTRUCTURE | 1.58 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00" x 4'00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Lalgola G.P, Paharpur G.P, Amdahara G.P, Kolan G.P, Kantanagar G.P, Mahammodpur G.P,Amarkundu G.P. & Shibpur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. , tno- 13/21-22/AE LSD |  |  | VCH/000821/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 07/10/2021 | S.S.INFRASTRUCTURE | 2.32 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Lalbagh Sub-Division under Murshidabad Division, P.H.E Dte.(Amdahara GP, Mahammadpur GP & Kantanagar GP), TNO-14/21-22/EE |  |  | VCH/000823/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 07/10/2021 | S.S.INFRASTRUCTURE | 3.26 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | IEC PROGRAM AND VIDEO DOCUMENTARY AND OTHER AWARENESS WORK OF FHTC AT DIFFERENT PLACES UNDER LSD |  |  | VCH/000589/2021-2022 |  | 24/09/2021 | 24/09/2021 | S.S.INFRASTRUCTURE | 9.91 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection (FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Lalbagh Sub-Division under Murshidabad Division, P.H.E Dte. (Shibpur G.P, Amarkundu G.P, Lalgola G.P. & Bilborakopra G.P., TNO- 15/21-22/AELSD |  |  | VCH/000822/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 07/10/2021 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Allied work for rectrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Babupur (Village Code-314126) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/001274/2021-2022 | 391/JSD | 31/12/2021 | 30/01/2022 | BENGAL ENTERPRISE | 4.83 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village LAKSHIJALA (Village Code 314127) under KASIADANGA Ground Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-II Block in the District of Murshidabad. Tender no - 550 of 21-22 by EE MURD |  |  | VCH/001465/2021-2022 | 362-MSD/21-22 | 11/03/2022 | 11/03/2022 | MARUTI CONSTRUCTION AND CO | 35.66 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Laying of UPVC pipeline at village LAXMIJOLA WEST SIDE in connection with FHTC work under KASIADANGA (ZONE-I) W/S Scheme under JSD PHE DTE. Tender no - 55 of 21-22 by AE LSD |  |  | VCH/000092/2022-2023 | 25-MSD/22-23(RE | 28/04/2022 | 28/04/2022 | PRADIP DAS | 4.67 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babupur ( Village Code 314126) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001756852) |  |  | VCH/001473/2021-2022 | 380-MSD/21-22 | 16/03/2022 | 16/03/2022 | BENGAL ENTERPRISE | 18.97 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Laying of UPVC pipeline at village LAXMIJOLA WEST SIDE in connection with FHTC work under KASIADANGA (ZONE-I) W/S Scheme under JSD PHE DTE. Tender no - 55 of 21-22 by AE LSD |  |  | VCH/000029/2022-2023 | 25-MSD/22-23 | 11/04/2022 | 11/04/2022 | PRADIP DAS | 4.67 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lakshijala ( Village Code -314127) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000075/2021-2022 | 1468/MURD | 21/06/2021 | 20/08/2021 | MARUTI CONSTRUCTION AND CO | 35.66 | 0 | 0 | 0
Total | [13 empty] | 125.88 | 0 | 0