## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Raghunathganj-II Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/001174/2021-2022 | 364/JSD | 22/12/2021 | 21/01/2022 | S.S.INFRASTRUCTURE | 3.13 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 06/21-22/AE-LSD |  |  | VCH/000867/2021-2022 | 205-MSD/21-22 | 08/12/2021 | 08/12/2021 | IMAGIN | 2.93 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-II ) TNO- 786/20-21/EE |  |  | VCH/000864/2021-2022 | 206-MSD/21-22 | 25/11/2021 | 25/11/2021 | MOTI RAHAMAN | 2.76 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of mouza Jhamra ( 314121 ) under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - I Block of Murshidabad District PHE DTE. (Scheme ID: 0001756852). Tender no 786 of 20-21 by EE |  |  | VCH/000190/2021-2022 | 16-MSD / 21-22 | 04/08/2021 | 04/08/2021 | MOTI RAHAMAN | 30.49 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-IV). | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/001761/2021-2022 | 127/JSD | 22/03/2022 | 21/04/2022 | MOTI RAHAMAN | 3.5 | 2.94 | 84.18 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-I). | ASSISTANT ENGINEER |  | ORD/001752/2021-2022 | 121/JSD | 22/03/2022 | 21/04/2022 | DIPAYAN DEY | 4.2 | 3.59 | 85.37 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-II). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001762/2021-2022 | 128/JSD | 22/03/2022 | 21/04/2022 | MURSHID ALOM | 3.87 | 3.83 | 98.85 | 90
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-III). | ASSISTANT ENGINEER |  | ORD/001760/2021-2022 | 126/JSD | 22/03/2022 | 21/04/2022 | DIPAYAN DEY | 3.73 | 3.53 | 94.48 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 540/11/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 2.2 | 0 | 0 | 0
Total | [13 empty] | 56.81 | 13.89 | 24.45