## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan of Togra (Village Code 315978) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no-736 of 20-21 by EE / MSD |  |  | VCH/000141/2021-2022 | null | 01/07/2021 |  | SUPTI ENTERPRISE | 7.26 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of Togra ( 315978 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-II ) TNO- 736/20-21/EE |  |  | VCH/000008/2021-2022 | 04/MSD/21-22 | 16/07/2021 |  | SUPTI ENTERPRISE | 7.26 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Retrofitting functional hoyusehold tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village MUNIADIHI under PANCHTHUPI Ground Based W/S Scheme for Arsenic Affected area of Burwan Block under MSD PHE DTE. Scheme Id:0007335523 in the dist of Murshidabad. Sl. No.23 Tender no 63 SE/MC 20-21 |  |  | VCH/000038/2021-2022 | 03/MSD/21-22 | 16/07/2021 |  | DECON INDIA | 23.9 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Muslim Para in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001189/2021-2022 | 322/KSD | 16/11/2021 | 16/12/2021 | APURBA SAHA CHOWDHURY | 4.83 | 4.79 | 99.23 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Chatterjee Para in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. Tender no: 39 of 21-22 by AE KSD |  |  | VCH/001423/2021-2022 | 356-MSD/21-22 | 05/03/2022 |  | DECON INDIA | 4.82 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MUNIADIHI under PANCHTHUPUI Ground Water Based Water Supply Scheme for arsenic affected areas of BURWAN Block under Murshidabad Div PHE DTE in the District of Murshidabad. Tender no - 63 of 20-21 by SE MC |  |  | VCH/001452/2021-2022 | 355-MSD/21-22 | 07/03/2022 |  | DECON INDIA | 15.99 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Laying of UPVC distribution pipeline for FHTC work at Mirjapara & Bagdipara in the Village of Muniadihi Panchthupi W/S Scheme under KSD PHE DTE. Tender no - 40 of 21-22 by AE KSD |  |  | VCH/001455/2021-2022 | 354-MSD/21-22 | 05/03/2022 |  | DECON INDIA | 4.81 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village TOGRA (Village Code 315978) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. |  |  | VCH/000534/2022-2023 | 192-MSD/22-23 | 29/06/2022 |  | SUPTI ENTERPRISE (PROP.DEBAPRIYA SAHA) | 3.11 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Muniadihi (Village Code- 315982) under Panchthupi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division, P.H.E.Dte. (SL-02) | ASSISTANT ENGINEER |  | ORD/000518/2022-2023 | 155/KSD | 31/08/2022 | 15/10/2022 | SARTHAK SK. | 4.81 | 3.17 | 65.84 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Restoration work of UPVC pipeline & road restoration work including laying of CI/DI pipeline for smooth supply of drinking water at Panchthuppi Bus Stand area under Panchthuppi Water Supply Scheme under Kandi Sub-Division, P.H.E. Dte.in the District Murshidabad | ASSISTANT ENGINEER |  | ORD/001136/2021-2022 | 320/KSD | 16/11/2021 | 16/12/2021 | SUPTI ENTERPRISE | 4.83 | 4.82 | 99.83 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Mirjapara & Bagdipara in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. |  |  | ORD/001191/2021-2022 | 324/KSD | 16/11/2021 | 16/12/2021 | DECON INDIA | 4.84 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/001230/2021-2022 | 214/KSD | 11/08/2021 | 10/09/2021 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | Retrofitting | Continuation order for Holding Awarness Programme / Campaigning programs at Chandpur-I II G.P, Bali G.P, Patikabari G.P, Madhupur G.P, Kedar Chandpur-I G.P, Khidirpur G.P, Humaipur G.P, Rampara-I G.P, Andulberia G.P, Dadpur G.P, Rampara-II G.P, Mirzapur-I & II G.P, Kumarpur Sujapur G.P, Debkunda G.P, Madda G.P, Sahajadpur G.P, Niyallishpara G.P, Satui Chowrigachha G.P, Shaktipur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000115/2020-2021 | 691/MURD | 23/02/2021 | 25/03/2021 | IMAGIN | 4.77 | 4.77 | 100 | 0
Total | [13 empty] | 95.57 | 17.55 | 18.36