## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | Retrofitting | Fault defection of Repairing or replacing the damaged material Pannel board submerssible pump existing chlorinetaror of other direc existing chlonator and other direc Mahadebnagar Z-II W/S Scheme under JSD PHE DTE. TNO- 41 of 21-22 by AE/JSD |  |  | VCH/000698/2021-2022 | 104-MSD/2021-22 | 20/09/2021 | 20/09/2021 | ARYA CONSTRUCTION | 3.81 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-III ) TNO- 764/20-21/EE |  |  | VCH/000009/2021-2022 |  | 12/04/2021 | 12/04/2021 | SOUMYA KANTI SINHA | 17.54 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | Retrofitting | Safe Drinking Water Supply (Modified ATU) arrangement for Char Sarandajpur Primary School under ISD under Murshidabad Div PHE DTE. Tender no - 74 of 21-22 by AE / ISD |  |  | VCH/000697/2021-2022 | 92-MSD/2021-22 | 20/09/2021 | 20/09/2021 | SARTHAK SK. | 4.76 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village SHIBARAMBATI (Village Code 315980) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000744/2020-2021 | 3034/MURD | 07/12/2020 | 21/01/2021 | SOUMYA KANTI SINHA | 18.57 | 0 | 0 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00 x 4'00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Nowda G.P, Raypur G.P, Madhupur G.P, Sarbangapur G.P, Choa G.P, Hariharpara G.P, Mahula G.P, Rampur-I & II G.P Rangamati Chandpara G.P. Satui Chowrigachha G.P, Shaktipur G.P. & Chhaighari G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000235/2021-2022 | 142/BSD | 21/06/2021 | 21/07/2021 | IMAGIN | 3.77 | 3.77 | 100 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00"x 4"00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Radharghat I & II G.P. Ramnagar Bachhara G.P, Sompara-I & II G.P, Doulatabad G.P, Mirzapur-I & II G.P, Kumarpur Sujapur G.P, Debkunda G.P, Madda G.P, Sahajadpur G.P & Niyallishpara G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000234/2021-2022 | 233/BSD | 14/07/2021 | 13/08/2021 | S.S.INFRASTRUCTURE | 3.77 | 1.43 | 37.8 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | Retrofitting | Balance Retrofitting Work of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under at Janardanpur & adjoining mouzas (JL NO-147) ( Village Code -315981) from the exiting distribution system of Panchthupi Water Supply Scheme (Ground Water Based) in Burwan Block under Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000409/2020-2021 | 534/MURD | 04/02/2021 | 05/04/2021 | J.S. CONSTRUCTION | 44.75 | 44.37 | 99.15 | 1
Total | [13 empty] | 96.98 | 49.57 | 51.11