## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHOWRIGACHHA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000522/2021-2022 | 353/BSD | 27/08/2021 | 26/09/2021 | TINA ROY | 4.16 | 4.16 | 100 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Satui (Village code 315341) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723177 in the District of Murshidabad.3136/MURD, 11/12/2020 |  |  | VCH/000674/2021-2022 | 172-MSD/21-22 | 01/11/2021 | 01/11/2021 | UTTAM MUKHERJEE | 32.45 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER |  | ORD/002071/2021-2022 | 106/BSD | 28/03/2022 | 27/04/2022 | CHOWDHURY CONSTRUCTION | 4.79 | 0.75 | 15.74 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2022 to 17.04.2023.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER |  | ORD/000623/2022-2023 | 205/JSD | 18/04/2022 | 18/04/2023 | MAJIBUR RAHAMAN | 4.76 | 1.6 | 33.59 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Continuation work for Hiring of 1 (one) no. Diesel Bolero/Marshal car (WB-57C 9120) for official use of the Assistant Engineer, Jangipur Sub Division, Murshidabad Division P.H.E. Dte. for the period from 01.03.2022 to 31.05.2022 (i.e) 3 (Three) months (vehicle No.-WB-57C/9120). | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/001722/2021-2022 | 88/JSD | 22/02/2022 | 22/05/2022 | MANUAR HOSSAIN | 0.45 | 0.23 | 49.6 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000135/2023-2024 | 165/ISD | 01/04/2023 | 01/10/2023 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 2.37 | 266.31 | 100
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting |  |  |  | BILL/00243/2023-2024 | 97-MSD/2023-24 | 08/06/2023 | 08/06/2023 | DULAL CHOWDHURY | 0.8 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year].for the month of April¿2023 to March¿2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000900/2022-2023 | 330/MURD | 07/02/2023 | 07/02/2024 | SOUMYADIP MISRA | 4.78 | 4.57 | 95.51 | 32
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2023 to 17.04.2024.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000093/2023-2024 | 437-/AA/JSD | 17/04/2023 | 16/04/2024 | MAJIBUR RAHAMAN | 4.76 | 2.79 | 58.58 | 70
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chhota Satui (Village code 315343) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID- 1723177 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000168/2021-2022 | 1651/MURD | 29/06/2021 | 26/12/2021 | DAS TRADING CO. | 80.05 | 104.67 | 130.75 | 1
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000456/2021-2022 | 306/BSD | 13/08/2021 | 12/09/2021 | IMAGIN | 3.26 | 6.51 | 200 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001777/2021-2022 | 106/BSD | 28/03/2022 | 27/04/2022 | CHOWDHURY CONSTRUCTION | 4.79 | 0 | 0 | 90
13 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01(One) Year] (period for i.e 07/02/2023 to 06/02/2024). | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE | ORD/000897/2022-2023 | 329/MURD | 07/02/2023 | 07/02/2024 | MD MUKLESUR RAHAMAN | 4.78 | 2.45 | 51.26 | 1
14 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 06 (Six) Months i.e. from 08.07.2023 to 07.01.2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000148/2023-2024 | 24/LSD | 30/06/2023 | 31/12/2023 | BARI ENTERPRISE | 0.9 | 2.24 | 249.17 | 100
15 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | ENGAGEMENT OF CAR FOR SE-MC, PHE DTE. |  |  | BILL/01173/2024-2025 | 342-MSD/2024-25 | 06/09/2024 | 06/09/2024 | SOUMYADIP MISRA | 0.21 | 0 | 0 | 0
16 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Satui (Village code 315341) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723177 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000186/2020-2021 | 3136/MURD | 11/12/2020 | 09/02/2021 | UTTAM MUKHERJEE | 39.68 | 2.19 | 5.52 | 1
17 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | Retrofitting | Extension of Distribution UPVC pipeline at Hanumandanga, Poradanga & Haldepara area for Providing Balance Functional Household Tap connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Choto Satui (Village Code-315343) under Bara Satui Ground water based water suply scheme for Arsenic affected areas of Berhampore Block, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/001807/2021-2022 | 768/MURD | 22/03/2022 | 21/04/2022 | DAS TRADING CO. | 42.34 | 27.11 | 64.03 | 1
Total | [13 empty] | 233.84 | 161.63 | 69.12