## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Nialispara ( village code: 315317 ) of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 18nos FHTC | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000193/2022-2023 | 202/BSD | 28/04/2022 | 28/05/2022 | SURAJIT MONDAL | 4.81 | 4.1 | 85.25 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tikiapara (Village code 315318) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005182920 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001468/2021-2022 | 281/MURD | 03/02/2022 | 04/04/2022 | M/S SWAPAN KUMAR NATH AND CO. | 19.7 | 18.08 | 91.77 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Nialispara ( village code: 315317 ) of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 28nos FHTC | ASSISTANT ENGINEER |  | ORD/000194/2022-2023 | 203/BSD | 28/04/2022 | 28/05/2022 | ABIDA CONSTRUCTION | 4.85 | 3.85 | 79.51 | 80
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000026/2021-2022 | 539/11/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 0.49 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 69 nos in connection with Jal Swapna (Jal Jeevan Mission ) including Laying of Distribution system of Nialispara ( Village Code -315317) under Budharpara Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000195/2022-2023 | 1185/MURD | 09/05/2022 | 08/06/2022 | AMAL KUMAR DAS | 37.93 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Laying distribution pipeline in connection with Jal Swapna (Jal Jeevan Mission) of Nialispara ( village code: 315317 ) and Budhorpara village of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000184/2022-2023 | 191/BSD | 28/04/2022 | 28/05/2022 | MOBIDUR RAHAMAN | 4.67 | 4.67 | 99.97 | 80
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Budharpara (Village code 315320) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte.Scheme ID - 5182920 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000443/2021-2022 | 2644/MURD | 27/08/2021 | 26/10/2021 | M/S. BIMALENDU BOSE | 21.87 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gopjan (Village code 315447) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005182920 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000001/2022-2023 | 1126/MURD | 29/04/2022 | 13/06/2022 | PRATICHI ENTERPRISE | 24.48 | 0 | 0 | 40
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 67 nos in connection with Jal Swapna (Jal Jeevan Mission ) including Laying of Distribution system of Raniswar( Village Code -315314) under Budharpara Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000030/2022-2023 | 1083/MURD | 27/04/2022 | 27/05/2022 | DEBASISH SARKAR | 33.33 | 0 | 0 | 1
Total | [13 empty] | 152.12 | 30.7 | 20.18