## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniara Masadda (VILL CODE-315905) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric (PART-I) tNO- 791/20-21/EE |  |  | VCH/000266/2021-2022 | 41-MSD / 21-22 | 24/08/2021 | 24/08/2021 | DEBASISH SARKAR | 9.94 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Laying of parallel UPVC pipeline from Masadda Shib Mandir to Masadda Durga Mandir for FHTC work of Raniara Masadda village (Village Code- 315905) of Burwan Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000007/2022-2023 | 09 / KSD | 06/04/2022 | 06/05/2022 | S.K. ENTERPRISE (PROP:SHAMIM ISLAM) | 4.82 | 0 | 0 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhanghara (315950) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric. Tender no - 850 of 20-21 by EE MURD |  |  | VCH/001454/2021-2022 | 343-MSD/21-22 | 05/03/2022 | 05/03/2022 | DAS CONSTRACTION (MUNNA DAS) | 5.48 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Hiring of 1 (One) no Diesel Scorpio car for fJangipur Sub Div. under MSD PHE DTE. Period 01.04.2022 to 10.06.2022 |  |  | VCH/000554/2022-2023 | 200-MSD/2022-23 | 06/07/2022 | 06/07/2022 | MADAN MOHAN SASMAL | 0.41 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhanghara (315950) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric (PART-I) |  |  | VCH/001297/2021-2022 |  | 17/02/2022 | 17/02/2022 | DAS CONSTRACTION | 5.48 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Laying of parallel UPVC pipeline from Masadda Bus Stand to Masadda Shib Mandir for FHTC work of Raniara Masadda village (Village Code- 315905) of Burwan Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. |  |  | VCH/000536/2022-2023 | 194-MSD/22-23 | 30/06/2022 | 30/06/2022 | MAA CONSTRUCTION (NAJMUL HAQUE) | 4.58 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000416/2021-2022 | 216/KSD | 11/08/2021 | 10/09/2021 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BURWAN-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000462/2021-2022 | 231/KSD | 27/08/2021 | 26/10/2021 | M/S. S. DAS AND ENTERPRISE | 4.17 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BURWAN-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000463/2021-2022 | 232/KSD | 27/08/2021 | 26/10/2021 | IMAGIN COMMUNICATION | 4.17 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Holding Awarness Programme / Campaigning programms at Burwan-I & II G.P, Sahora G.P, Panchthupi G.P and Sabalpur G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-C). | ASSISTANT ENGINEER (HQ) |  | ORD/000555/2021-2022 | 251/KSD | 31/08/2021 | 30/09/2021 | IMAGIN COMMUNICATION | 3.99 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SAHORA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000475/2021-2022 | 243/KSD | 27/08/2021 | 26/10/2021 | IMAGIN | 4.17 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Rameswarpur habitation under Rameswarpur Village Code-315954(JL NO-120) Burwan Water Supply Scheme (Ground Water Based) under Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000260/2020-2021 | 2391/MURD | 18/09/2020 | 02/11/2020 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.77 | 0 | 0 | 1
13 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 15/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
14 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/00974/2023-2024 |  | 14/12/2023 | 14/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
15 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village RANIARA MASADDA (Village Code 315905) under Burwan Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000156/2020-2021 | 3219/MURD | 18/12/2020 | 16/02/2021 | DEBASISH SARKAR | 12.49 | 0 | 0 | 0
16 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Rameswarpur habitation under Rameswarpur Village Code-315954(JL NO-120) Burwan Water Supply Scheme (Ground Water Based) under Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000629/2020-2021 | 2391/MURD | 18/09/2020 | 02/11/2020 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.77 | 0 | 0 | 1
Total | [13 empty] | 178.31 | 0 | 0