## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAHARA (Village Code 315291) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000385/2020-2021 | 3021/MURD | 04/12/2020 | 18/01/2021 | M/S. BIMALENDU BOSE | 25.13 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of BHANDIRA habitation under Bhandira (Village Code: 315292) under BAHARA Surface Water Based Water Supply Scheme for arsenic affected areas of KANDI Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 398 of 20-21 by EE / MSD |  |  | VCH/000198/2021-2022 | 08 -MSD / 21-22 | 04/08/2021 |  | M/S GUNGUN CONSTRUCTION | 22.54 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village LAHARPARA (Village Code 315282) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000585/2020-2021 | 2880/MURD | 12/11/2020 | 27/12/2020 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 32.21 | 8.94 | 27.77 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00'' x 4'00'') which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Gokarna-II G.P, Mahalandi-I G.P, Kumarsanda G.P, Jasahari Anukha-I & II G.P, Burwan- I & II G.P, Panchthupi G.P & Sohara G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000078/2021-2022 | 176/KSD | 28/05/2021 | 27/06/2021 | IMAGIN | 2.61 | 2.61 | 100 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAHARA (Village Code 315291) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000185/2020-2021 | 3021/MURD | 04/12/2020 | 18/01/2021 | M/S. BIMALENDU BOSE | 25.13 | 24.83 | 98.8 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Laying of different dia UPVC pipe line from node point 45 to node point 3 & node point 45 to node point 1E for distribution network with supply of materials for pipe line under Improvement work of Bahara water supply scheme under Kandi Sub Division, P.H.E.Dte in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000727/2020-2021 | 3222/MURD | 18/12/2020 | 17/01/2021 | KUNTAL SAHA | 4.86 | 4.85 | 99.98 | 1
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) of Bahara & Ghoshbati habitation under command area of Bahara village (Village Code- 315291) of Bahara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Kandi Block under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad.(SL_03) | ASSISTANT ENGINEER |  | ORD/000519/2022-2023 | 156/KSD | 31/08/2022 | 15/10/2022 | SIMA ENTERPRISE | 4.84 | 4.8 | 99.02 | 1
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Laying of different dia UPVC pipeline for distributin network Part-B with supply of materials for pipe line at construction of RCC stand post including platform under improvement work of Bahara W/S Scheme under Kandi sub div phe dte. | ASSISTANT ENGINEER |  | ORD/000616/2019-2020 | 1558/MURD | 27/06/2019 |  | M/S. BIMAL MISRA | 8.03 | 8.03 | 100 | 1
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Laying of rising main (DI) from tube well to 300 Cum OHR and laying of distribution main (DI) from OHR to distribution system including supply of C.I. specials and restoration work of concrete road of Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000003/2022-2023 | 05/KSD | 06/04/2022 | 06/05/2022 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.85 | 4.59 | 94.76 | 1
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Construction of valve chamber & laying of upvc pipe line including supply of C.I. specials and valves in connection with FHTC work of Bahara village (Village Code-315810) under Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. (SL-01) | ASSISTANT ENGINEER |  | ORD/000517/2022-2023 | 154/KSD | 31/08/2022 | 30/09/2022 | BISWAS CONSTRUCTION | 4.55 | 4.54 | 99.76 | 1
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Laying of pipe line for distribution system from node point 1B to 1C & laying of rising main from H.W Site to 2nd tube well site under Improvement work of Bahara water supply scheme under Kandi Sub Division, P.H.E.Dte in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000707/2020-2021 | 3109/MURD | 09/12/2020 | 08/01/2021 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.84 | 4.81 | 99.47 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000415/2021-2022 | 215/KSD | 11/08/2021 | 10/09/2021 | IMAGIN COMMUNICATION | 4.33 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JASAHARI ANUKHA-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000441/2021-2022 | 225/KSD | 27/08/2021 | 26/10/2021 | IMAGIN | 4.17 | 0 | 0 | 0
14 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at GOKARNA-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000474/2021-2022 | 242/KSD | 27/08/2021 | 26/10/2021 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0 | 0
15 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JASAHARI ANUKHA-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000457/2021-2022 | 226/KSD | 27/08/2021 | 26/10/2021 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0 | 0
Total | [13 empty] | 156.41 | 68.01 | 43.48