## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | Retrofitting | Replacement of media for Renovation of I.E Plant at Arjunpur W/S Scheme, of Jangipur Sub-Division under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000564/2022-2023 | 2941/MURD | 03/11/2022 | 23/11/2022 | SUMAN ENTERPRISE AND SUMAN AQUA | 10.21 | 8.65 | 84.7 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-24 |  |  | VCH/000986/2022-2023 | 399-MSD/22-23 | 18/11/2022 | 18/11/2022 | EASTERN RAILWAY (MALDA DIVISION) | 2.57 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-19 |  |  | VCH/000984/2022-2023 | 399-MSD/22-23 | 18/11/2022 | 18/11/2022 | EASTERN RAILWAY (MALDA DIVISION) | 6.19 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) of Mouja Bhabanipur (Village Code-313820), of Arjunpur &adjoining mouja under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0005184170) | ASSISTANT ENGINEER |  | ORD/000374/2022-2023 | 2086/MURD | 27/07/2022 | 24/11/2022 | DIPAYAN DEY | 88.99 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | Retrofitting | Continuation work order for Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/16 & 247/18) at Bhabanipur mouza & Connecting with existing 140 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000092/2023-2024 | 1607/MURD | 09/06/2023 | 08/08/2023 | PRADIP KUMAR DAS | 3.68 | 3.68 | 100 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | Retrofitting | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/16 & 247/18) at Bhabanipur mouza & Connecting with existing 140 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/001654/2021-2022 | 508/MURD | 23/02/2022 | 24/04/2022 | PRADIP KUMAR DAS | 36.8 | 36.8 | 100 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | Retrofitting | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/30 & 247/32) at Bhabanipur mouza & Connecting with existing 110 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/001655/2021-2022 | 509/MURD | 23/02/2022 | 24/04/2022 | M/S GUHA & ROY ENTERPRISE | 37.5 | 23.75 | 63.33 | 0
Total | [13 empty] | 185.93 | 72.88 | 39.2