## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/07678 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) in Connection with Jal Jeevan Mission & Jal Swapna of village of Momenpur Village Code (314732) Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District. PHE DTE Tender no-117 of 20-21 by SE / MC |  |  | VCH/000191/2021-2022 |  | 13/07/2021 | 13/07/2021 | M/S. BIMALENDU BOSE | 60.35 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/07678 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mamenpur (Village code 314732) under Mamenpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 000958860 (Sl No-13) |  |  | VCH/000022/2022-2023 | 22-MSD/22-23 | 14/04/2022 | 14/04/2022 | M/S. BIMALENDU BOSE | 4.42 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/07678 | Retrofitting | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Connection of different existing PWSS (Bhagirathpur PWSS Scheme,Block- Domkal)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 375 of 21-22 by EE MSD, and Scheme Code: 7678 |  |  | VCH/000036/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 14/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.73 | 0 | 0 | 0
Total | [13 empty] | 69.5 | 0 | 0