## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | Retrofitting | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS MITHIPUR PWSS Scheme, Block-RAGHUNATHGAUNGE-II to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/001141/2021-2022 | 3252/MURD | 05/10/2021 | 04/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.65 | 11.29 | 200 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of MITHIPUR (Village code 314136) under MITHIPUR Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005186173 | ASSISTANT ENGINEER |  | ORD/001154/2021-2022 | 3974/MURD | 21/12/2021 | 19/06/2022 | M/S. SINHA & SONS | 108.7 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KASIADANGA ZONE-II PWSS Scheme, Block - Raghunathganj-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 420 of 21-22 by EE MURD |  |  | VCH/001371/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 07/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.65 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KASIADANGA ZONE-II PWSS Scheme, Block - Raghunathganj-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 419 of 21-22 by EE MURD |  |  | VCH/001369/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 07/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.54 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | Retrofitting | HIRING OF CAR FOR JANGIPUR SUB DIVISION, PHE DTE. |  |  | BILL/00066/2022-2023 |  | 09/12/2022 | 09/12/2022 | MADAN MOHAN SASMAL | 0.42 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barala (Village code 314009) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-9) | ASSISTANT ENGINEER | Junior Engineer | ORD/000294/2020-2021 | 48/MURD | 06/01/2021 | 05/07/2021 | M/S UNIVERSAL TRADING | 63.12 | 14.5 | 22.98 | 100
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 540/12/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 15.81 | 0 | 0 | 0
Total | [13 empty] | 208.89 | 25.8 | 12.35