## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | SM/07767 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection of different existing PWSS Scheme, Block-SUTI-I to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 402 of 21-22 by EE MURD |  |  | VCH/001447/2021-2022 | 301-MSD/21-22 | 04/02/2022 |  | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.77 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | SM/07767 | Retrofitting | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion 90 mm dia U.P.C Pipe in between N.P 3(Pry. School) to N.P 12 via N.P 15 upto N.P 16(Bansabati G.P Member Loton Sara's House) for smooth water supply arrangement in Raturi Zone-2 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000293/2021-2022 | 198/JSD | 30/07/2021 | 29/08/2021 | GAUTAM KUMAR CHAUDHURI | 3.81 | 3.81 | 99.98 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | SM/07767 | Retrofitting | Laying of U.P.V.C New Extention pipeline of 90 mm dia in between N.P 6(Durga Mandir) to N.P 12 Upto Pond for smooth water supply arrangement in Raturi Zone-2 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000296/2021-2022 | 199/JSD | 30/07/2021 | 14/08/2021 | GAUTAM KUMAR CHAUDHURI | 1.43 | 1.43 | 99.95 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | SM/07767 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) | ASSISTANT ENGINEER |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 27/08/2022 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | SM/07767 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000465/2020-2021 | 547/MURD | 05/02/2021 | 07/03/2021 | PRADIP KUMAR DAS | 39.01 | 26.23 | 67.22 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | SM/07767 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 3632/C/MURD | 23/11/2021 |  | Resource Division | 22.88 | 0 | 0 | 0
Total | [13 empty] | 405.5 | 31.46 | 7.76