## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) | SM/07768 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SALAR (Village Code 315742) under SALAR Ground Water Based Water Supply Scheme for arsenic affected areas of BHARATPUR-II Block in the District of Murshidabad. Tender no - 127 of 21-22 by SE MC |  |  | VCH/000065/2022-2023 | 84-MSD/22-23 | 28/04/2022 | 28/04/2022 | MAMATA USHA ENTERPRISE | 38.32 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) | SM/07768 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SALAR G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000468/2021-2022 | 236/KSD | 27/08/2021 | 26/10/2021 | IMAGIN | 4.15 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) | SM/07768 | Retrofitting | Holding Awarness Programme / Campaigning programms at Salar G.P, Talibpur G.P, Kagram G.P, Tenya Baidyapur G.P and Simulia G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-D). | ASSISTANT ENGINEER (HQ) |  | ORD/000556/2021-2022 | 252/KSD | 31/08/2021 | 30/09/2021 | IMAGIN | 4 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) | SM/07768 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of SALAR (Village code 315742) under SALAR Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte.( Scheme ID 0005252601) | ASSISTANT ENGINEER |  | ORD/001163/2021-2022 | 3975/MURD | 21/12/2021 | 19/06/2022 | MAMATA USHA ENTERPRISE | 153.26 | 102.61 | 66.95 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) | SM/07768 | Retrofitting | Repairing of rising main & distribution line at Rail gate & Block road etc with construction of thrust block & laying of pipe line of new habitation of Salar Water Supply scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000871/2021-2022 | 296/KSD | 07/10/2021 | 06/11/2021 | DAS CONSTRACTION (MUNNA DAS) | 4.1 | 0 | 0 | 10
Total | [13 empty] | 203.84 | 102.61 | 50.34