## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P | SM/07772 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khidir Para ( Village Code -314739) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | ASSISTANT ENGINEER | Junior Engineer | ORD/000513/2020-2021 | 580/MURD | 09/02/2021 | 10/04/2021 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 33.55 | 33.54 | 99.99 | 80
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P | SM/07772 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DEPUTIPAR (Village Code-314582) under GODHANPARA Ground Water Supply Scheme for Arsenic Affected Area of RANINAGAR-II BLOCK under Murshidabad Division, PHE Dte. |  |  | VCH/000235/2021-2022 | 31-MSD / 21-22 | 27/08/2021 | 27/08/2021 | M/S ROY & BOSE ENTERPRISE | 10.92 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P | SM/07772 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Raypur (Village code-314582) under KatakobraGround Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0005185646) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000549/2022-2023 | 2765/MURD | 29/09/2022 | 27/01/2023 | SOFIQUL ISLAM | 154.82 | 144.08 | 93.06 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P | SM/07772 | Retrofitting | Repairing & Renovation of the Boundary wall of pump House No-2 Both & Allied works under Katakopra Zone- I & II water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad | ASSISTANT ENGINEER |  | ORD/002122/2021-2022 | 48/ISD | 28/01/2022 | 27/02/2022 | PARTHA RAJAK | 1.95 | 1.94 | 99.36 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P | SM/07772 | Retrofitting | Repairing & Renovation of the pump House No-1 & 2 under Katakopra Zone-I water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad | ASSISTANT ENGINEER |  | ORD/001240/2021-2022 | 46/ISD | 28/01/2022 | 29/03/2022 | PRAVAT KUMAR GHOSH | 3.65 | 3.64 | 99.79 | 1
Total | [13 empty] | 204.89 | 183.2 | 89.42