## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi | SM/07774 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26), 557/MURD, 08/02/2021 |  |  | VCH/000778/2021-2022 | 186-MSD/21-22 | 12/11/2021 | 12/11/2021 | MAMATA USHA ENTERPRISE | 35.48 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi | SM/07774 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26), TNO-107/20-21/SE-MC |  |  | VCH/000308/2022-2023 | 116-MSD/22-23 | 06/05/2022 | 06/05/2022 | MAMATA USHA ENTERPRISE | 42.57 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi | SM/07774 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000152/2020-2021 | 557/MURD | 08/02/2021 | 07/08/2021 | MAMATA USHA ENTERPRISE | 144.81 | 93.66 | 64.68 | 0
Total | [13 empty] | 222.87 | 93.66 | 42.03