## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) | SM/07908 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village HARI SANKARPUR (Village code 314740) under KATAKOBRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of DOMKAL Block, under Murshidabad Division, PHE Dte. Scheme ID 0005185646 in the District of Murshidabad. Tender no 827 of 20-21 by EE MSD |  |  | VCH/000270/2021-2022 |  | 18/08/2021 | 18/08/2021 | M/S SUBHA CONSTRUCTION | 32.45 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) | SM/07908 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village HARI SANKARPUR (Village code 314740) under KATAKOBRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of DOMKAL Block, under Murshidabad Division, PHE Dte. Scheme ID 0005185646 in the District of Murshidabad. Tender no 827 of 20-21 by EE MSD |  |  | VCH/000722/2021-2022 | 51-MSD/21-22 | 13/09/2021 | 13/09/2021 | M/S SUBHA CONSTRUCTION | 32.45 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) | SM/07908 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hari Sankarpur ( Village Code -314740) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | ASSISTANT ENGINEER | Junior Engineer | ORD/000743/2020-2021 | 651 /MURD | 18/02/2021 | 19/04/2021 | M/S SUBHA CONSTRUCTION | 43.8 | 0 | 0 | 1
Total | [13 empty] | 108.71 | 0 | 0