## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07909 | Retrofitting | Extension of pipeline from different (Juranpur & Tekaraipur) water supply scheme forn connection of Health Centre under Domkal & Raninagar-I Block under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000319/2021-2022 | 380/1/ISD | 26/07/2021 | 25/08/2021 | M/S. SAJEDA ENTERPRISE | 4.02 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07909 | Retrofitting | Extension of pipeline from different (Shibnagar laskarpur, juranpur, Juginda Zone-II, Tekaraipur, Garibpur Z-I, Aminabad) water supply scheme forn connection of Health Centre under Domkal & Raninagar-I Block under Islampur Sub-Division under Murshidabad Division, PHE Dte | ASSISTANT ENGINEER |  | ORD/002124/2021-2022 | 381/1/ISD | 26/07/2021 | 25/08/2021 | NABIRUL ISLAM | 4.14 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07909 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1467 nos in connection with (Jal Jeevan Mission ) and under command area of village of Juranpur ( Village Code -314720) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000204/2022-2023 | 1380/MURD | 26/05/2022 | 25/07/2022 | M/S. S. DAS AND ENTERPRISE | 72.04 | 0 | 0 | 40
Total | [13 empty] | 80.21 | 0 | 0