## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | Work of Laying of U.P.V.C. Pipe line at Sikdarpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/002103/2021-2022 | 387 /JSD | 31/12/2021 | 30/01/2022 | DEBOJYOTI CONSTRUCTION | 4.63 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | CONTINUATION ORDER OF CAR HIRING OF AE-LSD 261/LSD DATE- 04/03/2021 |  |  | VCH/001017/2022-2023 | 359-MSD/22-23 | 19/10/2022 | 19/10/2022 | ARINDAM MAJUMDAR | 0.61 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | HIRING OF CAR FOR SE-MC |  |  | VCH/001016/2022-2023 | 358-MSD/22-23 | 19/10/2022 | 19/10/2022 | HASNA BEWA | 0.6 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | Continuation work order for Hiring of 1 no of Car for official use of the eAE LSD PHE DTE. Work Order No 261 / LSD DATE 04.03.2021 |  |  | VCH/000598/2022-2023 | 202-MSD/2022-23 | 07/07/2022 | 07/07/2022 | ARINDAM MAJUMDAR | 1.08 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | Work order for Hiring of 1 no of Car for official use of the AE JSD PHE DTE. Work Order No 302 / JSD. DATE 25.11.2021 |  |  | VCH/000638/2022-2023 | 205-MSD/2022-23 | 08/07/2022 | 08/07/2022 | MANUAR HOSSAIN | 1.19 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | Work order for Hiring of 1 no of Car for official use of the AE ISD PHE DTE. Work Order No 473 / ISD. DATE 03.09.2021 |  |  | VCH/000641/2022-2023 | 206-MSD/22-23 | 12/07/2022 | 12/07/2022 | M/S SAJAHAN CHOWDHURY | 0.78 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | work order for Hiring of 1 no of Car for official use of the SE MC PHE DTE. Work Order No 10 / MC. DATE 05.01.2022 |  |  | VCH/000599/2022-2023 | 203-MSD/2022-23 | 07/07/2022 | 07/07/2022 | HASNA BEWA | 0.62 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 540/3/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 2.7 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | Rail Bhoomi Crossing Seva (IR-RBCS) Eastern Railway Howrah Division DEMAND NOTE Application ID: ER-HWH-2024-WL-64 |  |  | BILL/01535/2024-2025 | 545-MSD/2024-25 | 28/10/2024 | 28/10/2024 | EASTERN RAILWAY (HOWRAH DIVISION) | 0.11 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 492 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Sikdarpur ( Village Code -313858) under Sikdarpur & adjoining mouzas Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000049/2022-2023 | 1115/MURD | 29/04/2022 | 29/05/2022 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 26.22 | 0 | 0 | 0
Total | [13 empty] | 38.54 | 0 | 0