## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | SM/07917 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village DAKSHIN NAGAR (Village Code: 314728) under JUGINDA Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 003 of 20-21 by EE / MSD |  |  | VCH/000226/2021-2022 | 17-MSD / 21-22 | 13/08/2021 | 13/08/2021 | SUJIT KUMAR SAHA | 36.26 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | SM/07917 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of village JHAUBARIA (Village Code: 314729) under JUGINDA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL, Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID : 0001723344) Tender no- 825 of 20-21 by EE / MURD |  |  | VCH/000189/2021-2022 | 15-MSD / 21-22 | 10/08/2021 | 10/08/2021 | DAS ENTERPRISE (SUBRATA DAS) | 14.24 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | SM/07917 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jhaubaria ( Village Code -314729) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344). | ASSISTANT ENGINEER |  | ORD/000729/2020-2021 | 584/MURD | 09/02/2021 | 10/04/2021 | DAS ENTERPRISE (SUBRATA DAS) | 21.07 | 0 | 0 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | SM/07917 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Nagar ( Village Code -314728) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723344). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000740/2020-2021 | 594 / MURD | 09/02/2021 | 10/04/2021 | SUJIT KUMAR SAHA | 46.24 | 0 | 0 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | SM/07917 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Nagar ( Village Code -314728) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723344). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000171/2020-2021 | 594/MURD | 09/02/2021 | 10/04/2021 | SUJIT KUMAR SAHA | 46.24 | 0 | 0 | 1
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | SM/07917 | Retrofitting | Relaying of different dia UPVC pipeline for Balance Providing Functional Household Tap connection (FHTC) of 94 nos in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Jhaubaria (Village Code-314729) under Juginda Ground water based water suply scheme for Arsenic affected areas of DomkalBlock, under Murshidabad Division, P.H.E. Dte. (scheme ID- 0001723344) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001835/2021-2022 | 767/MURD | 22/03/2022 | 11/04/2022 | MONDAL ENTERPRISE | 6.65 | 0 | 0 | 1
Total | [13 empty] | 170.7 | 0 | 0