## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mridadpur (314570) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-II | SM/07920 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mridadpur ( Village Code -314570) under Brindabanpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0005019111). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000183/2020-2021 | 597/MURD | 09/02/2021 | 10/04/2021 | SANJAY BISWAS | 67.55 | 68.85 | 101.93 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mridadpur (314570) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-II | SM/07920 | Retrofitting | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 493 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mridadpur (Village code 314570) under Brindabanpur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005019111) | ASSISTANT ENGINEER |  | ORD/001879/2021-2022 | 855/MURD | 31/03/2022 | 20/04/2022 | SUBHENDRA MOHAN SARKAR | 12.24 | 0 | 0 | 100
Total | [13 empty] | 79.79 | 68.85 | 86.29