## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) | SM/07926 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Fatepur (Village code 315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723484 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000511/2020-2021 | 78/MURD | 08/01/2021 | 09/03/2021 | RELIABLE ENTERPRISE | 26.51 | 20.89 | 78.78 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) | SM/07926 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KHIDIRPUR G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000500/2021-2022 | 335/BSD | 27/08/2021 | 26/09/2021 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) | SM/07926 | Retrofitting | Additional Laying and distribution of UPVC pipiline for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of FATEPUR ( Village Code _315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000186/2022-2023 | 193/BSD | 28/04/2022 | 28/05/2022 | S.G CONSTRUCTION , | 4.36 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) | SM/07926 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000447/2021-2022 | 297/BSD | 13/08/2021 | 12/09/2021 | IMAGIN | 4.34 | 4.34 | 100 | 0
Total | [13 empty] | 39.37 | 25.22 | 64.06