## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/08099 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (Jal Jeevan Mission ) and under command area of village of Bhatsala ( Village Code -314688) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) TNO- 165/21-22/EE |  |  | VCH/001499/2021-2022 | 413-MSD/21-22 | 22/03/2022 | 22/03/2022 | MAMON ENTERPRISE AND CONSTRUCTION (MASIUR RAHAMAN MOLLA) | 27.35 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/08099 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village Juginda (Village code 314727)under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723344) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000224/2022-2023 | 1468/MURD | 03/06/2022 | 01/10/2022 | SUJIT KUMAR SAHA | 130.65 | 78.95 | 60.43 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/08099 | Retrofitting | Protection of Over Head Reservoir by Masonry wall & construction of entrance gate of Head work site premises under Juginda Z-I Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/002123/2021-2022 | 475/ISD | 03/09/2021 | 02/11/2021 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 3.64 | 3.64 | 99.95 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/08099 | Retrofitting | Protection of Head work site & Pump House No-II premises by raising Boundary wall height by R.B.T fencing under Juginda Z-I Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/002130/2021-2022 | 474/ISD | 03/09/2021 | 02/11/2021 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.7 | 4.69 | 99.87 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/08099 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (Jal Jeevan Mission ) and under command area of village of Bhatsala ( Village Code -314688) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000056/2021-2022 | 1349/MURD | 09/06/2021 | 08/08/2021 | MAMON ENTERPRISE AND CONSTRUCTION (MASIUR RAHAMAN MOLLA) | 77.6 | 82.67 | 106.55 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/08099 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000455/2021-2022 | 305/BSD | 13/08/2021 | 12/09/2021 | IMAGIN COMMUNICATION | 4.33 | 8.67 | 200 | 0
Total | [13 empty] | 248.28 | 178.62 | 71.95