## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BABALTALI (Village Code 314583) under (SAIKHPARA AND BABALTALI adjoining habitation SAIKHPARA Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 360 of 21-22 by EE MURD |  |  | VCH/001513/2021-2022 | 415-MSD/21-22 | 22/03/2022 | 22/03/2022 | MITRA CONSTRUCTION | 45.89 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Kartekerpara & Lalchandabad) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | VCH/001530/2021-2022 | 438-MSD/21-22 | 30/03/2022 | 30/03/2022 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 51.77 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Babaltali ( Village Code -314583)( Nojorana&Panipia& adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000489/2021-2022 | 2680/MURD | 31/08/2021 | 30/10/2021 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 97.62 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000448/2021-2022 | 298/BSD | 13/08/2021 | 12/09/2021 | S.S.INFRASTRUCTURE | 4.34 | 4.34 | 100 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Extension of Distribution UPVC pipeline and providing balance Functional Household Tap Connections (FHTC) of 633 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari (Villagecode-314589)(Katlamari, Ramnagarpara & adjoining habitation) under Seikhpara Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0006086670) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001805/2021-2022 | 854/MURD | 31/03/2022 | 15/04/2022 | HIRANMAY GHOSH | 8.27 | 0 | 0 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari ( Village Code -314589) (Mohongonj &Kaharpara & adjoining habitation) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | ASSISTANT ENGINEER | Junior Engineer | ORD/001714/2021-2022 | 716/MURD | 15/03/2022 | 14/05/2022 | SOFIQUL ISLAM | 80.52 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Jhaubaria (Village Code -314585) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006086670) | ASSISTANT ENGINEER | Junior Engineer | ORD/000290/2021-2022 | 2297/MURD | 02/08/2021 | 01/10/2021 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 97.86 | 43.69 | 44.65 | 1
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari (Village Code -314589)(Katlamari & Ramnagarpara& adjoining habitation) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000291/2021-2022 | 2298/MURD | 02/08/2021 | 01/10/2021 | HIRANMAY GHOSH | 97.89 | 58.99 | 60.26 | 100
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Kartekerpara & Lalchandabad) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000437/2021-2022 | 2641/MURD | 27/08/2021 | 26/10/2021 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 97.88 | 0 | 0 | 70
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | Retrofitting | Extension of Distribution UPVC pipeline for providing Balance Functional Household Tap Connections (FHTC) of 1180 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jhaubaria (Village code 314585) under Saikhpara Area Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0006086670). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001716/2021-2022 | 703/MURD | 14/03/2022 | 29/03/2022 | AZAD ENTERPRISE | 12.2 | 0 | 0 | 0
Total | [13 empty] | 594.23 | 107.01 | 18.01