## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Joypur (Village code 315086) under Bhalkundi (Zone-I) Ground Water Based water Supply Scheme for Arsenic Affected Area of Khargram Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154928 in the District of Murshidabad. (Sl No-08) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000306/2020-2021 | 165/MURD | 15/01/2021 | 14/07/2021 | SOUMYADIP MISRA | 56.13 | 50.3 | 89.61 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village TELSUNDI (Village Code 315121) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000516/2020-2021 | 3020/MURD | 04/12/2020 | 18/01/2021 | M/S GUNGUN CONSTRUCTION | 19.58 | 0 | 0 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAUTIPARA (Village Code 315089) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000526/2020-2021 | 3026/MURD | 04/12/2020 | 18/01/2021 | SOM CONSTRUCTION AGENCY | 15.45 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bhalkundi(Village code 315091) under Bhalkundi (Zone-II)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Khargram Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154928 in the District of Murshidabad. (Sl No-09) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000553/2020-2021 | 3045/MURD | 07/12/2020 | 05/06/2021 | M/S BHUBAN DAS | 47.51 | 0 | 0 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village Palsanda (315119) of Bhalkundi under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram Block of Murshidabad District . Tender no 540 of 20-21 by EE |  |  | VCH/000596/2021-2022 | 143-MSD/21-22 | 11/10/2021 |  | M/S. GOURI ENTERPRISE | 32.46 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Balance FHTC works of extension of distribution pipeline and restoration works of damage pipeline at Bhalkundi (Zone-II) Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad | ASSISTANT ENGINEER |  | ORD/001137/2021-2022 | 318/KSD | 16/11/2021 | 16/12/2021 | M/S BHUBAN DAS | 4.77 | 4.77 | 99.94 | 1
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with 'JALSWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BAUTIPARA (Village Code 315089) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. Tender no - 694 of 20-21 by EE MURD |  |  | VCH/001445/2021-2022 | 334-MSD/21-22 | 05/03/2022 |  | SOM CONSTRUCTION AGENCY | 3.38 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Balance work of distribution pipeline at Shri Krishnapur Village under Bhalkundi (Zone-I) Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001195/2021-2022 | 337/KSD | 30/11/2021 | 30/12/2021 | SOUMYADIP MISRA | 4.8 | 4.8 | 99.98 | 1
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Laying of HDPE (Materials grade PE-100 & Pressure Rating: PN6) pipe line & allied works of Retrofitting of Functional Household Tap Connections (FHTC) at village Bhalkundi (Village code-315091) Bhalkundi water supply scheme for FHTC work under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000025/2022-2023 | 29/KSD | 08/04/2022 | 08/05/2022 | TIRUPATI CONSTRUCTION | 4.59 | 4.11 | 89.57 | 1
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Laying of HDPE (Materials grade PE -100 & Pressure Rating : PN 6) Pipe Line due to widening of PWD Roads & construction of drain at village Bhalkundi (Village Code-315091) under Bhalkundi Water Supply Scheme of Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000227/2022-2023 | 98 / KSD | 06/06/2022 | 06/07/2022 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 4.83 | 4.56 | 94.36 | 1
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Providing Balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of PALSANDA ( Village Code -315119) under Bhalkundi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001808/2021-2022 | 818/MURD | 25/03/2022 | 24/04/2022 | M/S. GOURI ENTERPRISE | 9.52 | 9.38 | 98.46 | 1
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JOYPUR G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000461/2021-2022 | 230/KSD | 27/08/2021 | 26/10/2021 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000043/2021-2022 | 541/3/MURD | 25/02/2022 |  | Resource Division | 2.7 | 0 | 0 | 0
Total | [13 empty] | 209.89 | 77.92 | 37.12