## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village SUNIA (Village Code 315806) under Bharatpur Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-I Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000571/2020-2021 | 3037/MURD | 07/12/2020 | 21/01/2021 | NAMDAR ALI | 8.6 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village LAKSHIJALA (Village Code 314127) under KASIADANGA Ground Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-II Block in the District of Murshidabad. Tender no - 550 of 21-22 by EE MURD |  |  | VCH/001466/2021-2022 | 366-MSD/21-22 | 11/03/2022 |  | NAMDAR ALI | 4.55 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Extension of UPVC pipeline for FHTC work at Daspara, Ghoshpara, Kurulpara, Anchalpara, Gobardhanpara and Bagdipara in the Village of Alugram of Bharatpur Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000009/2022-2023 | 11 / KSD | 06/04/2022 | 06/05/2022 | M/S. RAHAMAN CONSTRUCTION CO | 4.84 | 4.83 | 99.91 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Laying of parallel distribution pipe line in between node point 15F to 23A and extension of distribution pipe line left & right side of canal of Alugram village (Village Code-315806) of Bharatpur water supply scheme for FHTC work under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000005/2022-2023 | 07 / KSD | 06/04/2022 | 06/05/2022 | AGNIBESH CHATTERJEE | 4.84 | 4.84 | 99.87 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Repairing of rising main pipe line including supplying of C.I specials, valves, construction of valve chamber & surface drain for the FHTC work of Bharatpur water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. (SL-04) | ASSISTANT ENGINEER |  | ORD/000520/2022-2023 | 157/KSD | 31/08/2022 | 30/09/2022 | PRANAB KUMAR GHOSH | 4.77 | 4.74 | 99.56 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at ALUGRAM G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000466/2021-2022 | 234/KSD | 27/08/2021 | 26/10/2021 | IMAGIN | 4.17 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Holding Awarness Programme / Campaigning programms at Alugram G.P, Bharatpur G.P and Sijgram G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 12 nos) (Part-E). | ASSISTANT ENGINEER (HQ) |  | ORD/000557/2021-2022 | 253/KSD | 31/08/2021 | 30/09/2021 | S.S.INFRASTRUCTURE | 2.4 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SIJGRAM G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000472/2021-2022 | 240/KSD | 27/08/2021 | 26/10/2021 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Madanpur Dafarpur ( Village Code -315810) under BHARATPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0007336059) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001718/2021-2022 | 731/MURD | 16/03/2022 | 30/04/2022 | MOTI RAHAMAN | 40.35 | 10.42 | 25.81 | 45
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 541/2/MURD | 25/02/2022 |  | Resource Division | 5.12 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Alugram under Bharatpur Ground Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0007336059 in the District of Murshidabad. (Sl No-18) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000288/2020-2021 | 3270/MURD | 24/12/2020 | 22/06/2021 | M/S . SUKUMAR SINHA | 109.97 | 77.74 | 70.69 | 100
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | Retrofitting | Supplying of C.I specials, valves & construction of valve chamber of different location for FHTC work of Alugram village of Bharatpur water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000627/2022-2023 | 3182/MURD | 30/11/2022 | 20/12/2022 | U.S BUILDERS | 4.97 | 4.77 | 95.98 | 100
Total | [13 empty] | 198.75 | 107.34 | 54.01