## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-A). | ASSISTANT ENGINEER |  | ORD/001259/2021-2022 | 379/JSD | 31/12/2021 | 30/01/2022 | S.D PROJECT | 4.77 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-B). | ASSISTANT ENGINEER |  | ORD/001260/2021-2022 | 380/JSD | 31/12/2021 | 30/01/2022 | S.D PROJECT | 4.77 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Sinking of (300 mm x 200 mm) dia Big dia tube well 75 mtr. Deep by direct rotary rig method using UPVC Pipe and RDS filter at Village Kankuria (Village Code-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme (Scheme ID- 0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000093/2022-2023 | 239/JSD | 05/05/2022 | 04/06/2022 | MOTI RAHAMAN | 4.42 | 0 | 0 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Supply of UPVC Pipe and RDS filter for the work of Sinking of (300 mm x 200 mm) dia Big dia tube well at Village Kankuria (Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme (Scheme Id:-0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000094/2022-2023 | 240/JSD | 05/05/2022 | 04/06/2022 | MOTI RAHAMAN | 4.6 | 0 | 0 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-C) | ASSISTANT ENGINEER |  | ORD/001288/2021-2022 | 395/JSD | 31/12/2021 | 30/01/2022 | M/S. SRM ENTERPRISE | 4.77 | 4.17 | 87.4 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-D) | ASSISTANT ENGINEER |  | ORD/001257/2021-2022 | 377/JSD | 31/12/2021 | 30/01/2022 | R.K.CONSTRUCTION(SOHEL RANA KHAN) | 4.77 | 4.76 | 99.91 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-G). | ASSISTANT ENGINEER |  | ORD/001759/2021-2022 | 125/JSD | 22/03/2022 | 21/04/2022 | YOUSUF ENTERPRISE | 4.8 | 4.6 | 95.92 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-E) | ASSISTANT ENGINEER |  | ORD/001749/2021-2022 | 118/JSD | 22/03/2022 | 21/04/2022 | S.D PROJECT | 4.85 | 4.85 | 100 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-F). | ASSISTANT ENGINEER |  | ORD/001750/2021-2022 | 119/JSD | 22/03/2022 | 21/04/2022 | S.D PROJECT | 4.84 | 4.84 | 99.93 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-H). | ASSISTANT ENGINEER |  | ORD/001751/2021-2022 | 120/JSD | 22/03/2022 | 21/04/2022 | S.D PROJECT | 4.76 | 4.73 | 99.36 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANKURIA (Village Code 313873) under KANKURIA AND JAFRABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 98 of 21-22 by AE JSD |  |  | VCH/001480/2021-2022 | 388-MSD/21-22 | 17/03/2022 | 17/03/2022 | S.D PROJECT | 4.77 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Village JAFRABAD (Village Code 313872) under KANKURIA and jafrabad Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 475 of 21-22 by EE MURD |  |  | VCH/001430/2021-2022 | 347-MSD/21-22 | 05/03/2022 | 05/03/2022 | NILKAMAL BASAK | 91.86 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANKURIA (Village Code 313873) under KANKURIA AND JAFRABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 98 of 21-22 by AE JSD |  |  | VCH/001481/2021-2022 | 389-MSD/21-22 | 17/03/2022 | 17/03/2022 | S.D PROJECT | 4.77 | 0 | 0 | 0
14 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) |  |  | VCH/001291/2021-2022 |  | 17/02/2022 | 17/02/2022 | NILKAMAL BASAK | 91.86 | 0 | 0 | 0
15 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 540/10/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 12.11 | 0 | 0 | 0
16 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jafrabad ( Village Code -313872) & (adjoining habitation) (Part-IV) under Kankuria & Jafrabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006303234) | ASSISTANT ENGINEER |  | ORD/000404/2021-2022 | 2536/MURD | 19/08/2021 | 18/10/2021 | M/S. M.R. CONSTRUCTION (PROP: MASUD RANA) | 67.49 | 0 | 0 | 0
17 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Jafrabad ( Village Code -313872 & adjoining habitation (Part-III) under Kankuria&Jafrabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006303234) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000409/2021-2022 | 2539/MURD | 19/08/2021 | 18/10/2021 | IKON CONSTRUCTION | 80.14 | 0 | 0 | 0
Total | [13 empty] | 400.34 | 27.95 | 6.98