## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BISHANNAGAR (Village Code 315605) under BELDANGA MUNICIPALITY Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-I Block in the District of Murshidabad. Tender no - 905 of 21-22 by EE MURD |  |  | VCH/001450/2021-2022 | 346-MSD/21-22 | 05/03/2022 | 05/03/2022 | NAYLA CONSTRUCTION | 79.01 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 539/10/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 10.18 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Debkunda (Village code-315602) under Madda Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-I Block of Murshidabad District under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000552/2022-2023 | 2833/MURD | 17/10/2022 | 14/02/2023 | AMAL KUMAR DAS | 119.55 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bishannagar ( Village Code -315605) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000287/2020-2021 | 599/MURD | 09/02/2021 | 10/04/2021 | NAYLA CONSTRUCTION | 95.64 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1851 nos in connection with (Jal Jeevan Mission ) and under command area of village of Debkunda ( Village Code -315602) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000111/2022-2023 | 1195/MURD | 10/05/2022 | 09/07/2022 | SOURAV DEY | 82.09 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Madda ( Village Code -315603) & adjoining habitation (Part-I) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000317/2021-2022 | 2385/MURD | 09/08/2021 | 08/10/2021 | MITRA & SARKAR CONSTRUCTION | 65.45 | 50.92 | 77.81 | 10
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Madda ( Village Code -315603)adjoining habitation under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000316/2021-2022 | 2384/MURD | 09/08/2021 | 08/10/2021 | MITRA & SARKAR CONSTRUCTION | 63.64 | 61.02 | 95.88 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dalua ( Village Code -315580) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904). | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000492/2020-2021 | 591/MURD | 09/02/2021 | 29/04/2025 | S. ROY & CO. | 51.49 | 23.92 | 46.46 | 100
Total | [13 empty] | 567.06 | 135.86 | 23.96