## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Laskarpur ( Village Code -313850) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0005019105) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000625/2020-2021 | 595/MURD | 09/02/2021 | 10/04/2021 | ARABINDA GHOSH | 71.56 | 38.55 | 53.87 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KANKURIA-JAFRABAD ZONE-I PWSS Scheme, Block - SAMSERGANJ to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 415 of 21-22 by EE MURD |  |  | VCH/001372/2021-2022 | 301-MSD/21-22 | 07/02/2022 |  | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 8.73 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KANKURIA-JAFRABAD ZONE-II PWSS Scheme, Block - SAMSERGANJ to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 408 of 21-22 by EE MURD |  |  | VCH/001374/2021-2022 | 301-MSD/21-22 | 07/02/2022 |  | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.72 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Samserganj Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/001176/2021-2022 | 365/JSD | 22/12/2021 | 21/01/2022 | IMAGIN COMMUNICATION | 2.77 | 0 | 0 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of DOGACHHI (Village code 313848) under DOGACHHI under Ground Water Based Water Supply Scheme (SAMSERGANJ Block) and BAHADURPUR (Village Code-313924) under BAHADURPUR Ground Water Based Water Supply Scheme for (SUTI-I BLOCK) Arsenic Affected Areas of under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/001438/2021-2022 | 557/MURD | 28/02/2022 | 27/08/2022 | M/S. NANDY ENTERPRISE | 268.47 | 73.74 | 27.47 | 1
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of DOGACHHI (Village code 313848) under DOGACHHI under Ground Water Based Water Supply Scheme (SAMSERGANJ Block) and BAHADURPUR (Village Code-313924) under BAHADURPUR Ground Water Based Water Supply Scheme for (SUTI-I BLOCK) Arsenic Affected Areas of under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/002129/2021-2022 | 557 /MURD | 28/02/2022 | 27/08/2022 | M/S. NANDY ENTERPRISE | 268.47 | 0 | 0 | 1
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 3632/A/MURD | 23/11/2021 |  | Resource Division | 18.39 | 0 | 0 | 0
Total | [13 empty] | 646.13 | 112.29 | 17.38