## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area | SM/08199 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Raghunathpur (Village code 314783) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756480 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000623/2020-2021 | 321/MURD | 28/01/2021 | 29/03/2021 | M/S BAPPA ENTERPRISE | 13.73 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area | SM/08199 | Retrofitting | New laying of different dia UPVC pipeline to restore the distribution system (Besides of Sukdevmati Bridge) in Retrofitting Providing Functional House Hold Tap Connection FHTC in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Chainpara (314804) under Herampur Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000351/2022-2023 | 302/ISD | 20/07/2022 | 19/08/2022 | PRATICHI ENTERPRISE | 3.31 | 2.86 | 86.22 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area | SM/08199 | Retrofitting | Providing Balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sitanagar ( Village Code -314802) under Herampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005183990) | ASSISTANT ENGINEER |  | ORD/001776/2021-2022 | 857/MURD | 31/03/2022 | 30/05/2022 | PRIYANKA CONSTRUCTION | 49.23 | 44.68 | 90.75 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area | SM/08199 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sitanagar ( Village Code -314802) under Herampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005183990). | ASSISTANT ENGINEER | Junior Engineer | ORD/000717/2020-2021 | 590/MURD | 09/02/2021 | 10/04/2021 | PRIYANKA CONSTRUCTION | 26.4 | 23.39 | 88.63 | 1
Total | [13 empty] | 92.67 | 70.93 | 76.54