## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari ( Village Code -314604)(Part-III) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) | ASSISTANT ENGINEER | Junior Engineer | ORD/000352/2021-2022 | 2501/MURD | 17/08/2021 | 16/10/2021 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 88.6 | 36.18 | 40.83 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Khairamari PWSS Scheme,Block- Jalangi) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 367 of 21-22 by EE MSD, and Scheme Code: 8200 |  |  | VCH/000039/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 14/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 8.31 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) |  |  | VCH/001294/2021-2022 |  | 17/02/2022 | 17/02/2022 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 9.83 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari (Village Code -314604)(Part-I) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) Tender no - 244 of 21-22 by EE MURD |  |  | VCH/001439/2021-2022 | 338-MSD/21-22 | 03/03/2022 | 03/03/2022 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 31.7 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harekrishnapur ( Village Code -314624) under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) Tender no - 243 of 21-22 by EE MURD |  |  | VCH/001385/2021-2022 | 333-MSD/21-22 | 25/02/2022 | 25/02/2022 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 9.83 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000449/2021-2022 | 299/BSD | 13/08/2021 | 12/09/2021 | IMAGIN COMMUNICATION | 4.34 | 8.67 | 200 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari (Village Code -314604)(Part-I) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000295/2021-2022 | 2300/MURD | 02/08/2021 | 01/10/2021 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 90.75 | 103.02 | 113.53 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari ( Village Code -314604)(Part-II) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000334/2021-2022 | 2435/MURD | 12/08/2021 | 11/10/2021 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 92.84 | 0 | 0 | 1
Total | [13 empty] | 336.19 | 147.87 | 43.99