## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tungi ( Village Code -315525) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000058/2021-2022 | 1211/MURD | 10/05/2021 | 09/07/2021 | MOTI RAHAMAN | 90.75 | 82.69 | 91.12 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Goghata ( Village Code -315526) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000435/2021-2022 | 1699/MURD | 07/07/2021 | 05/09/2021 | M/S JAN MOHAMMAD | 52.35 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | Providing 365 nos Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna within command area of village Tungi (Village code 315525) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186507 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001710/2021-2022 | 701/MURD | 14/03/2022 | 13/05/2022 | MOTI RAHAMAN | 98.18 | 49.92 | 50.85 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | AND REFILLING OF FILTER MEDIA WITH ALLIED WORKS OF IEP OF CHANDPUR WSS, TNO- 143/21-22/EE |  |  | VCH/000042/2022-2023 | 38-MSD/22-23 | 21/04/2022 |  | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna ( Jal Jeevan Mission) and under command area of village of Chandpur (Village code 315552)under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000284/2022-2023 | 1561/MURD | 16/06/2022 | 14/10/2022 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 126.1 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) village of Patikabari (Village Code-315550) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000522/2022-2023 | 2498/MURD | 30/08/2022 | 28/12/2022 | M/S. SINHA & SONS | 183.88 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | Repairing and Refilling of filter media with allied works of Iron Elemination Plant (I.E.P) at Chandpur W/S Scheme, under Berhampore Sub-Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/001345/2021-2022 | 12/BSD | 10/01/2022 | 25/01/2022 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 539/7/MURD | 25/02/2022 |  | Resource Division | 1.46 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | Retrofitting | Formal Work Order for :Augmentation of CHANDPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000359/2022-2023 | 2083/MURD | 27/07/2022 | 24/12/2022 | TINA ROY | 355.12 | 16.08 | 4.53 | 80
Total | [13 empty] | 917.54 | 148.69 | 16.21