## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bota, 314754 of Purushottampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-I), TNO- 929/20-21/EE |  |  | VCH/000655/2021-2022 | 127-MSD/21-22 | 07/10/2021 | 07/10/2021 | SINHA & COMPANY | 12.65 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Additional Works for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of BOTA ( Village Code -314754) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756484) | ASSISTANT ENGINEER |  | ORD/001245/2021-2022 | 52/ISD | 28/01/2022 | 27/02/2022 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 4.8 | 4.11 | 85.45 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MOLLADANGA (Village Code 314745) under PURUSOTTAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 17 of 21-22 by SE MC |  |  | VCH/001487/2021-2022 | 420-MSD/21-22 | 23/03/2022 | 23/03/2022 | M/S TRADE ASSOCIATE | 46.29 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village DURGAPUR (Village Code 314756) under PURUSOTTAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 291 of 20-21 by EE MURD |  |  | VCH/001510/2021-2022 | 405-MSD/21-22 | 23/03/2022 | 23/03/2022 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 31.84 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Extension of Distribution UPVC pipeline for Providing Balance Functional Household Tap Connections (FHTC) of 559 Nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Molladanga (Village code 314745) under Purusattampur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 000175684). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001701/2021-2022 | 671/MURD | 10/03/2022 | 09/04/2022 | S.K. ENTERPRISE (PROP:SHAMIM ISLAM) | 17.21 | 16.53 | 96.03 | 1
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Purushottampur (Village code 314753) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756484 in the District of Murshidabad. (Sl No-04) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000351/2021-2022 | 2502/MURD | 17/08/2021 | 15/12/2021 | SUJIT KUMAR SAHA | 85.13 | 134.17 | 157.59 | 1
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Molladanga (Village code 314745) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756484 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000411/2021-2022 | 2556/MURD | 23/08/2021 | 21/12/2021 | M/S TRADE ASSOCIATE | 69.82 | 15.24 | 21.83 | 1
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arizpur (Village code 314746) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad.¿ | ASSISTANT ENGINEER | Junior Engineer | ORD/000565/2020-2021 | 36/MURD | 05/01/2021 | 06/03/2021 | ARJU CONSTRUCTION | 5.82 | 5.43 | 93.38 | 1
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 235 nos household under command area of village of Uttar Gopalpur, Molladanga, Arizpur, Purandanpur, Purushottampur, Bota,Durgapur ( Village Code-314744, 314745, 314746, 314747, 314753, 314754, 314756) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001756484) | ASSISTANT ENGINEER |  | ORD/000129/2022-2023 | 1212/MURD | 10/05/2022 | 09/06/2022 | BARMAN ENTERPRISE | 12.4 | 0 | 0 | 1
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Uttar Gopalpur (Village code 314744) under Purusottampur and Jitpur Ground Water Based Water Supply Scheme under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000820/2020-2021 | 031/MURD | 05/01/2021 | 06/03/2021 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 9.28 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Durgapur( Village Code -314756) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar_I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756484) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000196/2021-2022 | 1747/MURD | 09/07/2021 | 07/09/2021 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 52.77 | 19.02 | 36.05 | 1
Total | [13 empty] | 348.02 | 194.5 | 55.89