## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Madna(CT) (Village code 313940) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000344/2021-2022 | 2476/MURD | 16/08/2021 | 15/10/2021 | NOVELTY CONSTRUCTION | 39.3 | 35.25 | 89.69 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gotha (Village code 313912) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000684/2020-2021 | 542 / MURD | 05/02/2021 | 06/04/2021 | SHIRSHENDU MUKHERJEE | 7.73 | 0 | 0 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 1837nos household under command area of village of Panchgachhia, Arazi Ramakantapur,Gotha,Sadkpur( Village Code-313919, 313910, 313912, 313920) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001756899) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000130/2022-2023 | 1214/MURD | 10/05/2022 | 09/07/2022 | SWAPAN DAS | 79.18 | 0 | 0 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sujanipara (313923) of Madna under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District (PART-I) |  |  | VCH/001288/2021-2022 |  | 17/02/2022 | 17/02/2022 | R.K. CONSTRUCTION | 33.77 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PANCHGACHHIA (Village Code 313919) under MADNA Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 790 of 20-21 by EE MURD |  |  | VCH/000294/2022-2023 | 104-MSD/22-23 | 06/05/2022 | 06/05/2022 | DIPAYAN DEY | 15.99 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SUJANIPARA (Village Code 313923) under MADNA Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 44 of 21-22 by EE MURD |  |  | VCH/001448/2021-2022 | 350-MSD/21-22 | 04/03/2022 | 04/03/2022 | R.K. CONSTRUCTION | 33.77 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sujanipara (Village code 313923) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000045/2020-2021 | 528/MURD | 04/02/2021 | 05/04/2021 | R.K. CONSTRUCTION | 33.78 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gotha (Village code 313912) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID : 0001756899 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000162/2020-2021 | 542/MURD | 05/02/2021 | 06/04/2021 | SHIRSHENDU MUKHERJEE | 7.73 | 7.46 | 96.56 | 1
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arazi Ramakantapur (Village code 313910) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000564/2020-2021 | 533/MURD | 04/02/2021 | 05/04/2021 | M H SUPPLIERS | 16.7 | 33.4 | 199.93 | 1
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sadikpur (Village code 313920) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000514/2020-2021 | 524/MURD | 04/02/2021 | 05/04/2021 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 33.02 | 32.9 | 99.64 | 1
Total | [13 empty] | 300.97 | 109.01 | 36.22