## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid | SM/08685 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents and Glassware for NABL accreditation at Murshidabad District Water Testing Laboratory under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/001128/2021-2022 | 274 /HQ | 08/11/2021 | 08/12/2021 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.17 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid | SM/08685 | Support-WQMSP | Chemical, glassware & instrumments requirment for NABL accreditation at Murshidabad District Water Testing Laboratory as per ISO/IEC: 17025: 2017 under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/001127/2021-2022 | 2728/MURD | 03/09/2021 | 13/09/2021 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 14.36 | 12.87 | 89.63 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid | SM/08685 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents and Glassware for NABL accreditation at Murshidabad District Water Testing Laboratory under Murshidabad Division, P.H.E.Dte. |  |  | VCH/000044/2022-2023 | 40-MSD/22-23 | 21/04/2022 | 21/04/2022 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.17 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid | SM/08685 | Support-WQMSP | Continuation Work Order for Engaging Chemist, Bacteriologist and Laboratory Assistant for test of Water samples at Jangipur (WTP) Laboratory under Murshidabad Division, P. H. Engineering Dte for 06(Six) months (Period from 01-06-2022 to 30-11-2022) | ASSISTANT ENGINEER |  | ORD/000546/2022-2023 | 1351/MURD | 24/05/2022 | 24/11/2022 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.06 | 0 | 0 | 0
Total | [13 empty] | 23.77 | 12.87 | 54.16