## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jamalpur (Village code 315469) under Kismat Imadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. Scheme ID - 5186280 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000614/2020-2021 | 3141 /MURD | 11/12/2020 | 09/02/2021 | MEGHNA CONSTRUCTION (PROP.: ASARUL HOQUE) | 38.95 | 65.41 | 167.93 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kismat Imadpur (Village code 315468) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.Scheme ID 5186280 (Sl-37) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000532/2020-2021 | 696/MURD | 24/02/2021 | 23/08/2021 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 162.04 | 138.1 | 85.23 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | HOLDING AWARENESS PROGRESS AT DIFFERENT G.P, TNO- 339/21-22/EE |  |  | VCH/000863/2021-2022 | 205-MSD/21-22 | 08/12/2021 | 08/12/2021 | IMAGIN | 3.51 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Boundary wall at Head works site for part (B) of Kismat Emadpur water supply Scheme under Berhampore Sub Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/001839/2021-2022 | 99/BSD | 22/03/2022 | 21/04/2022 | AZAD ENTERPRISE | 4.52 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Extension of UPVC pipeline for Functional Household Tap Connections (FHTC) under village of Baruipara (Village Code -315465) under KismatImadpur Water Supply Scheme under Berhampore Sub-Division under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000166/2022-2023 | 155/BSD | 12/04/2022 | 12/05/2022 | SAMAR MUKHERJEE | 4.82 | 3.39 | 70.29 | 1
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Extension of UPVC pipeline for Functional Household Tap Connections (FHTC) under village of Baruipara (Village Code -315465) under Kismat Imadpur Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000603/2022-2023 | 256/BSD | 31/05/2022 | 30/06/2022 | SAMAR MUKHERJEE | 4.51 | 4.5 | 99.82 | 1
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 539/4/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 18.8 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1428 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lalnagar ( Village Code -315471) under Kismat Emadpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000028/2022-2023 | 1055/MURD | 25/04/2022 | 24/06/2022 | M/S GUHA & ROY ENTERPRISE | 75.91 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Baruipara (Village code 315465) under Kismat Imadpur Ground Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. Scheme ID 5186280 in the District of Murshidabad. (Sl No-38) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000305/2020-2021 | 728/MURD | 25/02/2021 | 24/08/2021 | SAMAR MUKHERJEE | 53.09 | 49.81 | 93.82 | 1
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1994 nos in connection with Jal Swapna (Jal Jeevan Mission ) under command area of Village of Khidirpur ( Village Code -315469) under Kismat Emadpur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000026/2022-2023 | 1056/MURD | 25/04/2022 | 24/06/2022 | MAMATA USHA ENTERPRISE | 99.92 | 0 | 0 | 1
Total | [13 empty] | 466.06 | 261.21 | 56.05