## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Kandi block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-A). (For 2 nos AWC). | ASSISTANT ENGINEER |  | ORD/000598/2020-2021 | 79/KSD | 22/02/2021 | 24/03/2021 | BHOWMIK CONSTRUCTION | 3.87 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilitates of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Kandi block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-B). (For 2 nos AWC). | ASSISTANT ENGINEER |  | ORD/000600/2020-2021 | 80/KSD | 22/02/2021 | 24/03/2021 | BIJOY SINGHA | 3.87 | 0 | 0 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Burwan block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-A). (For 2 nos AWC). | ASSISTANT ENGINEER |  | ORD/000631/2020-2021 | 85/KSD | 22/02/2021 | 24/03/2021 | PRAVAT KUMAR GHOSH | 3.87 | 0 | 0 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Burwan block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-B). (For 2 nos AWC). | ASSISTANT ENGINEER |  | ORD/000711/2020-2021 | 86/KSD | 22/02/2021 | 24/03/2021 | PARTHA PRATIM DAS | 3.87 | 0 | 0 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Extension of UPVC Pipeline from existing piped water supply scheme & connection of street stand post & construction of soak well to different Anganwadi centers of Burwan block under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. (Part-A).( For 9 nos AWC). | ASSISTANT ENGINEER |  | ORD/000124/2020-2021 | 76/KSD | 22/02/2021 | 24/03/2021 | DAS CONSTRACTION | 4.82 | 0 | 0 | 1
6 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Laying of distribution system pipe line and connection with street stand post and Construction of soak well in connection with Dengue control for different Anganwadi Centres under Nowda Development Block (1) Tiakata daspara .2.) Tiakata . 3) Jamalpur 4) Tiakata Halderpara under Berhampore Sub division. P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000411/2020-2021 | 3298/MURD | 29/12/2020 | 13/01/2021 | MAA SANKARI ENTERPRISE | 3.33 | 0 | 0 | 1
7 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Extension of UPVC Pipeline from existing piped water supply scheme & connection of street stand post & construction of soak well to different Anganwadi centers of Burwan block under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. (Part-B).( For 9 nos AWC). | ASSISTANT ENGINEER |  | ORD/000622/2020-2021 | 77/KSD | 22/02/2021 | 24/03/2021 | U.S BUILDERS | 4.83 | 0 | 0 | 1
8 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Bharatpur-I block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-B). (For 2 nos AWC). | ASSISTANT ENGINEER |  | ORD/000658/2020-2021 | 82/KSD | 22/02/2021 | 24/03/2021 | PRADIP MAHATO | 3.87 | 0 | 0 | 1
9 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Repairing & renovation of existing Sajaldhara (AIRP), including sinking of 125 mm x 50 mm dia 60.0 mtr. Deep tubewell at 34 No Harekrishnapur ICDS Center Sajaldhara Prakalpa, Jalangi Block under Islampur Sub-Division under Murshidabad Division, PHE Dte | ASSISTANT ENGINEER |  | ORD/002055/2021-2022 | 42/ISD. | 28/01/2022 | 27/02/2022 | ARJU CONSTRUCTION | 4.47 | 0 | 0 | 1
10 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilieites of different Anganwandi centers by sinking of tube well instllation of submersible pump and construction of soad well of Burwan Blok under Kandi Sub Div Phe DTE. Tender no - 09 of 21-22 by AE KSD |  |  | VCH/001444/2021-2022 | 351-MSD/21-22 | 04/03/2022 | 04/03/2022 | PARTHA PRATIM DAS | 1.19 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of BHARATPUR-II BLOCK under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. Tender no - 18 of 21-22 by AE KSD |  |  | VCH/001370/2021-2022 | 312-MSD/21-22 | 17/02/2022 | 17/02/2022 | GOUTAM KUMAR CHAUDHURI | 3.82 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilieites of different Anganwandi centers by sinking of tube well instllation of submersible pump and construction of soak well of Burwan Blok under Kandi Sub Div Phe DTE. Tender no - 35 of 21-22 by AE KSD |  |  | VCH/001492/2021-2022 | 397-MSD/21-22 | 29/03/2022 | 29/03/2022 | PRAVAT KUMAR GHOSH | 3.59 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Extension of UPVC Pipeline from existing piped water supply scheme & connection of street stand post & construction of soak well to different Anganwadi centers of Bharatpur-II block under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. (Part-B). ( For 9 nos AWC). |  |  | VCH/000020/2022-2023 | 26-MSD/22-23 | 14/04/2022 | 14/04/2022 | DIPAK BHOWMIK | 4.82 | 0 | 0 | 0
14 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Extension of UPVC pipeline from existing piped water supply scheme and connection of street stand post and construction of soak well to diff Anganwadi centers of KSD PHE DTE. PART-A (FOR 9 NOS AWC). Tender no - 09 of 22-23 by AE KSD. |  |  | VCH/000663/2022-2023 | 211-MSD/22-23 | 18/07/2022 | 18/07/2022 | MARUTI CONSTRUCTION AND CO | 4.74 | 0 | 0 | 0
15 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Bharatpur-II block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-A). (For 2 nos AWC). |  |  | VCH/001373/2021-2022 | 313-MSD/21-22 | 17/02/2022 | 17/02/2022 | M/S. ADHIKARY CONSTRUCTION | 3.79 | 0 | 0 | 0
16 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Extension of piped water supply to Anganwadi Centres(AWCs) located within the command area of PWS scheme at i) Suti -II block, (ii) Sagardighi block,(iii) Bharatpur -II block, (iv) Bharatpur -I block ,(v) Raghunathganj-I Block, (vi) Suti-I Block (vii) Raninagar -II Block,(viii) Raghunathganj-II Block ,(ix) Nabagram block, (x) Samserganj Block & (xi) Kandi block under Murshidabad Division, P.H.E. Dte. In the district Murshidabad. Tender no - 20 of 21-22 by SE MC |  |  | VCH/001461/2021-2022 | 367-MSD/21-22 | 11/03/2022 | 11/03/2022 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 129.4 | 0 | 0 | 0
17 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Extension of UPVC Pipeline from existing piped water supply scheme & connection of street stand post & construction of soak well to different Anganwadi centers of Bharatpur-I block under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. (Part-A). (For 9 nos AWC). | ASSISTANT ENGINEER |  | ORD/000051/2020-2021 | 73/KSD | 22/02/2021 | 24/03/2021 | GHOSH BUILDERS | 4.81 | 0 | 0 | 0
18 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Formal work order for extension of piped water supply to Anganwadi Centres (AWCs) located within the command area of PWS scheme at i) Domkal block,(ii) Jalangi block,(iii) Burwan block, (iv) Nowda block & (v) Raninagar-I Block under Murshidabad Division,P.H.E. Dte. In the district Murshidabad. | ASSISTANT ENGINEER |  | ORD/000419/2021-2022 | 2597/MURD | 25/08/2021 | 21/02/2022 | NAYLA CONSTRUCTION | 262.69 | 0 | 0 | 1
19 | MURSHIDABAD |  | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | Anganwadi | Formal work order for Extension of piped water supply to Anganwadi Centres(AWCs) located within the commandarea of PWS scheme at i) Suti -II block,(ii) Sagardighi block,(iii) Bharatpur -II block, (iv) Bharatpur -I block ,(v)Raghunathganj-I Block,(vi) Suti-I Block (vii) Raninagar -II Block,(viii) Raghunathganj-II Block ,(ix) Nabagram block, (x)Samserganj Block & (xi) Kandi block under Murshidabad Division,P.H.E. Dte. In the district Murshidabad | ASSISTANT ENGINEER |  | ORD/001186/2021-2022 | 1933/MURD | 22/07/2021 | 18/01/2022 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 466.68 | 0 | 0 | 1
Total | [13 empty] | 922.35 | 0 | 0