## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 3233/B/MURD | 02/12/2022 | 02/12/2022 | Resource Division | 46.99 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-16 |  |  | VCH/000762/2022-2023 | 290-MSD/22-23 | 20/09/2022 | 20/09/2022 | EASTERN RAILWAY (MALDA DIVISION) | 4.08 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-18 |  |  | VCH/000761/2022-2023 | 290-MSD/22-23 | 20/09/2022 | 20/09/2022 | EASTERN RAILWAY (MALDA DIVISION) | 40.56 | 0 | 0 | 0
4 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 2780/H/MURD | 01/10/2022 | 01/10/2022 | Resource Division | 40.23 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 2662/MURD | 20/09/2022 | 20/09/2022 | Resource Division | 98.85 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 1167/MURD/6 | 28/04/2023 | 28/04/2023 | Resource Division | 99.41 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Quotation payment for New Connection (Hizol P/H No.- II). |  |  | BILL/00034/2023-2024 | 36/DW-JJM | 18/05/2023 | 18/05/2023 | WBSEDCL | 0.84 | 0 | 0 | 0
8 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | rESTORATION OF DAMAGE PORTION LYING OF PHE PIPE LINE OF HIZOLE UNDER MSD HIGHWAY DIV-II |  |  | BILL/00960/2023-2024 |  | 12/12/2023 | 12/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
9 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-II). |  |  | BILL/00002/2023-2024 | 26/DW-JJM | 10/05/2023 | 10/05/2023 | WBSEDCL | 0.83 | 0 | 0 | 0
10 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Quotation payment for New Connection (Hizol P/H No.- I). |  |  | BILL/00032/2023-2024 | 35/DW-JJM | 18/05/2023 | 18/05/2023 | WBSEDCL | 0.84 | 0 | 0 | 0
11 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-III). |  |  | BILL/00003/2023-2024 | 27/DW-JJM | 10/05/2023 | 10/05/2023 | WBSEDCL | 0.83 | 0 | 0 | 0
12 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-I). |  |  | BILL/00004/2023-2024 | 28/DW-JJM | 10/05/2023 | 10/05/2023 | WBSEDCL | 0.83 | 0 | 0 | 0
13 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Quotation payment for New Connection (Hizol P/H No.- III). |  |  | BILL/00033/2023-2024 | 37/DW-JJM | 18/05/2023 | 18/05/2023 | WBSEDCL | 0.84 | 0 | 0 | 0
14 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Formal Work Order for Laying of Distribution System & rising main including all type of specials,valves,street stand post and FHTC Work in all complete for Hizole (Zone-II) Water Supply Scheme under Murshidabad Division, P.H.Engg Dte.at Kandi Block, Murshidabad District. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000355/2022-2023 | 1992/MURD | 21/07/2022 | 18/11/2022 | M/S. S. DAS AND ENTERPRISE | 501.06 | 338.5 | 67.56 | 1
15 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Formal Work Order for Laying of Distribution System & rising main including all type of specials,valves,street stand post and FHTC Work in all complete for Hizole (Zone-I) Water Supply Scheme under Murshidabad Division, P.H.Engg Dte.at Kandi Block, Murshidabad District. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000336/2022-2023 | 1723/MURD | 04/07/2022 | 01/11/2022 | M/S. TAPAS KUMAR CHAKRABORTY | 676.45 | 329.64 | 48.73 | 1
16 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | SHIFTING OF 11KV AT HIZOL |  |  | BILL/01583/2023-2024 | 450/WBSEDCL-JJM | 15/03/2024 | 15/03/2024 | WBSEDCL | 0.97 | 0 | 0 | 0
17 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III , Zone-I under Hizole ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000088/2023-2024 | 1933/MEDB | 16/06/2023 | 02/01/2025 | CONCORD ENGINEERING | 33.21 | 0 | 0 | 40
18 | MURSHIDABAD | Kandi | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.- I , II & III , Zone-II under Hizole ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000090/2023-2024 | 1934/MEDB | 16/06/2023 | 31/12/2025 | M/S SAJAHAN CHOWDHURY | 33.19 | 26.68 | 80.38 | 42
19 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Construction of 700 Cum OHR, Boundary Wall (H.W, 2nd & 3rd Site), Pump House (H.W, 2nd & 3rd Site), Land Development (H.W, 2nd & 3rd Site) and office cum godown of HIZOLE (Zone- I) & its adjoining mouzas water supply scheme of Kandi Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000596/2023-2024 | 3342/MURD | 28/10/2023 | 01/04/2026 | M/S JATIN | 374.61 | 69.73 | 18.61 | 5
20 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Construction of 600 Cum OHR, Boundary Wall (H.W, 2nd & 3rd Site), Pump House (H.W, 2nd & 3rd Site), Land Development (H.W, 2nd & 3rd Site) and office cum godown of HIZOLE (Zone- II) & its adjoining mouzas water supply scheme of Kandi Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000597/2023-2024 | 3344/MURD | 28/10/2023 | 31/03/2026 | M/S JATIN | 345.77 | 187.74 | 54.3 | 20
21 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Balance work for Extension of UPVC Pipeline and Road restoration work at different location of Hizole Zone -II Water Supply Scheme in Kandi Block of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000250/2024-2025 | 227/MURD | 27/01/2025 | 13/03/2025 | M/S. S. DAS AND ENTERPRISE | 91.04 | 0 | 0 | 0
22 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Allied works Pertaining to Construction of Cross Drain , Surface Drain, Office cum godown, Steel Structure Shade of Hizole-I PWSS at Kandi of Kandi-Sub Division under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000193/2024-2025 | 3211/MURD | 09/12/2024 | 01/12/2025 | M/S JATIN | 53.73 | 0 | 0 | 10
23 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Balance work for repair of road, construction of approach road & land development of Hizole-I & II & Bundai Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000006/2025-2026 | 835/MURD | 11/04/2025 | 01/12/2025 | M/S JATIN | 69.3 | 0 | 0 | 5
24 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Sinking of 3 nos of 200 mm dia (through) and 80.0 mtr. deep tube well drilling by direct rotary method at Head work site ,2nd Site & 3rd site of Hizole( Zone-I) Water Supply Scheme of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001756/2021-2022 | 782/MURD | 23/03/2022 | 22/04/2022 | MAMATA USHA ENTERPRISE | 16.77 | 15.6 | 93.01 | 1
25 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Sinking of 3 nos of 200 mm dia (through) and 80.0 mtr. deep tube well drilling by direct rotary method at Head work site, 2nd Site & 3rd site of Hizole( Zone-II) Water Supply Scheme of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001739/2021-2022 | 783/MURD | 23/03/2022 | 22/04/2022 | NADIA TUBEWELLS | 16.75 | 16.36 | 97.69 | 1
26 | MURSHIDABAD | Kandi | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | New | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well , 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & Hizole Water Supply Scheme at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000034/2023-2024 | 1109/MURD | 24/04/2023 | 16/04/2025 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0 | 100
Total | [13 empty] | 2604 | 984.26 | 37.8